## Dashboard
Automated Payment System — Development & QA Dashboard
Live register for delivery phases, test execution, acceptance gates and evidence. Update source sheets; dashboard formulas recalculate.
Metric | Current | Phase 01 release-readiness snapshot
Validated phases | 2 | Functional suite | 28 passed | Passed | 90.59% coverage | 2026-08-28
Total phases | 10 | Database recovery | Backup/restore | Passed | Revision and sampled counts matched | 2026-08-28
Passed tests | 55 | Session resilience | Concurrency/restart | Passed | Distinct sessions; restart continuity | 2026-08-28
Failed tests | 0 | Python dependencies | pip-audit | Passed | No known vulnerabilities | 2026-08-28
Blocked tests | 1 | Frontend dependencies | pnpm audit | Passed | No known vulnerabilities | 2026-08-28
|  | Browser matrix | Chrome + in-app | Accepted limitation | Firefox/Safari required before production promotion | 2026-08-28
|  | Test result | Count
|  | Passed | 55
|  | Failed | 0
|  | Blocked | 1
Current environment
|  | Branch | codex/backend-integration | Commit | 44e876e
|  | Frontend | codex/frontend-only-prototype @ 7043f0f | Status | Standalone mock validated
|  | API | http://127.0.0.1:8002 | Status | Healthy
|  | Database | PostgreSQL 16 on 127.0.0.1:5434 | Migration | 20260826_0004
|  | Evidence | docs/phase-01-plan.md | Updated | 2026-08-28

## Phase Register
Phase Register
Status and acceptance boundary for every planned implementation phase.
Phase ID | Phase | Scope Summary | Status | Acceptance Gate | Validation Reference | Last Validated | Owner | Notes
P00 | Foundation | API foundation, PostgreSQL, migrations, seed, middleware, CI/CD and hybrid frontend status | Validated | All foundation gates pass locally and in CI | docs/phase-00-validation.md | 2026-08-25 | Backend Team | Commit 4ddd199; local Docker validation complete
P01 | Authentication and RBAC | Local auth, sessions, users, roles, permissions and authorization | Validated | Protected endpoints enforce identity, role and department boundaries | docs/phase-01-plan.md | 2026-08-28 | Backend Team | 28 tests passed; 90.59% coverage; clean Python/frontend audits; Chrome/in-app UI and XLSX integrity passed. Firefox, Safari, penetration, and production proxy/HTTPS checks are accepted production-promotion limitations.
P02 | Master Data | Departments, cost centers, vendors, accounts, tax codes, currencies and payment methods | Not Started | Reference data is persisted, validated and safely administered | PROJECT_MANIFEST.md |  | Backend Team | Sensitive bank details encrypted and masked
P03 | Payment Requests | Drafts, request types, numbering, line items, allocations, submission and locking | Not Started | Every request type persists and enforces ownership and totals | PROJECT_MANIFEST.md |  | Backend Team | Includes optimistic locking and duplicate checks
P04 | Documents | Private files, metadata, checksum, replacement, rules, preview and review | Not Started | Protected document lifecycle works against persisted requests | PROJECT_MANIFEST.md |  | Backend Team | Malware scanning adapter required for production
P05 | Workflow and Approvals | Routes, assignments, queues, decisions, delegation, rerouting and immutable events | Not Started | Backend state machine rejects invalid or duplicate transitions | PROJECT_MANIFEST.md |  | Backend Team | Policy snapshot required at submission
P06 | Finance and Vouchers | VAT/EWT, accounting entries, validation, voucher snapshots and certification | Not Started | Balanced entries and approved persisted vouchers are enforced | PROJECT_MANIFEST.md |  | Backend Team | Financial calculations require boundary tests
P07 | Payment Execution | Payment attempts, authorization, processing, release, retries, voids and replacements | Not Started | Segregation of duties and immutable payment history pass | PROJECT_MANIFEST.md |  | Backend Team | Support partial and multiple attempts
P08 | Notifications and Reporting | Outbox, delivery history, dashboards, tracker, aging, exports and reports | Not Started | Durable notifications and reconciled report totals pass | PROJECT_MANIFEST.md |  | Backend Team | Development mailbox before production email
P09 | Administration and Integrations | Policies, retention, monitoring, SAML, storage, ERP, banking and webhooks | Not Started | Adapters are replaceable, monitored and safely configurable | PROJECT_MANIFEST.md |  | Backend Team | Production ownership decisions required

## Development Log
Development Log
Implemented work and planned development items, linked to branch, build and evidence.
Dev ID | Phase | Work Item | Area | Type | Status | Branch | Commit | Evidence | Owner | Updated | Notes
DEV-0001 | P00 | Versioned API routing | FastAPI | Feature | Complete | codex/backend-integration | 4ddd199 | /api and /api/v1/system/status | Backend Team | 2026-08-25 | API discovery and versioned system route
DEV-0002 | P00 | Liveness and readiness | Operations | Feature | Complete | codex/backend-integration | 4ddd199 | /healthz and /readyz | Backend Team | 2026-08-25 | Readiness checks PostgreSQL independently
DEV-0003 | P00 | PostgreSQL 16 Compose service | Database | Infrastructure | Complete | codex/backend-integration | 4ddd199 | docker-compose.yml | Backend Team | 2026-08-25 | Persistent local volume and health check
DEV-0004 | P00 | SQLAlchemy and Psycopg foundation | Database | Feature | Complete | codex/backend-integration | 4ddd199 | api/payment_module/database.py | Backend Team | 2026-08-25 | Session and rollback conventions
DEV-0005 | P00 | Alembic foundation migration | Database | Migration | Complete | codex/backend-integration | 4ddd199 | 20260819_0001 | Backend Team | 2026-08-25 | Creates plural system_settings table
DEV-0006 | P00 | Deterministic seed | Database | Feature | Complete | codex/backend-integration | 4ddd199 | python -m payment_module.seed | Backend Team | 2026-08-25 | Four idempotent system settings
DEV-0007 | P00 | Problem responses | API | Middleware | Complete | codex/backend-integration | 4ddd199 | application/problem+json | Backend Team | 2026-08-25 | Standardized 404 and request ID
DEV-0008 | P00 | Correlation IDs and logging | Operations | Middleware | Complete | codex/backend-integration | 4ddd199 | X-Request-ID | Backend Team | 2026-08-25 | Structured request logs
DEV-0009 | P00 | CORS configuration | Security | Middleware | Complete | codex/backend-integration | 4ddd199 | Origin http://127.0.0.1:5175 | Backend Team | 2026-08-25 | Configurable comma-separated origins
DEV-0010 | P00 | Philippine timezone | Platform | Convention | Complete | codex/backend-integration | 4ddd199 | Asia/Manila | Backend Team | 2026-08-25 | API and database session aligned
DEV-0011 | P00 | Hybrid frontend adapter | Frontend | Feature | Complete | codex/backend-integration | 4ddd199 | API connected indicator | Frontend Team | 2026-08-25 | Mock, hybrid and API modes
DEV-0012 | P00 | Backend CI and packaging | Delivery | CI/CD | Complete | codex/backend-integration | 4ddd199 | GitHub run 32719293106 | Backend Team | 2026-08-24 | Test and package jobs successful
DEV-0013 | P00 | Local Docker validation | Delivery | Environment | Complete | codex/backend-integration | 4ddd199 | Docker 29.6.2 / WSL 2.7.12 | Paolo Ylag | 2026-08-25 | PostgreSQL and API containers healthy
DEV-0014 | P01 | Identity and RBAC schema | Database | Migration | Complete | codex/backend-integration | a796a43 | 20260825_0002 | Backend Team | 2026-08-26 | Users, departments, roles, permissions, sessions and audit events
DEV-0015 | P01 | Requestor-manager association | Identity | Migration | Complete | codex/backend-integration | a796a43 | 20260825_0003 | Backend Team | 2026-08-26 | Self-assignment and manager cycles rejected
DEV-0016 | P01 | Local authentication and sessions | Security | Feature | Complete | codex/backend-integration | a796a43 | api/payment_module/routers/auth.py | Backend Team | 2026-08-26 | Local password authentication remains available with future SAML
DEV-0017 | P01 | Role and permission enforcement | Security | Feature | Complete | codex/backend-integration | a796a43 | api/payment_module/security.py | Backend Team | 2026-08-26 | Explicit user deny overrides role grants
DEV-0018 | P01 | User administration CRUD | Administration | Feature | Complete | codex/backend-integration | a796a43 | /api/v1/users | Backend Team | 2026-08-26 | Create, edit, delete, suspend and manager assignment
DEV-0019 | P01 | Role and permission CRUD | Administration | Feature | Complete | codex/backend-integration | a796a43 | /api/v1/roles and /api/v1/permissions | Backend Team | 2026-08-26 | Deletion safeguards preserve assigned access records
DEV-0020 | P01 | Department administration CRUD | Administration | Feature | Complete | codex/backend-integration | a796a43 | /api/v1/departments | Backend Team | 2026-08-26 | Initial departments plus audited future additions
DEV-0021 | P01 | Append-only identity audit | Audit | Feature | Complete | codex/backend-integration | a796a43 | api/payment_module/audit.py | Backend Team | 2026-08-26 | Actor, entity, request ID and before/after values recorded
DEV-0022 | P01 | Retained-session cleanup safeguards | Security | Maintenance | Complete | codex/backend-integration | a796a43 | 20260826_0004 / maintenance.py | Backend Team | 2026-08-26 | Disabled by default; hard-refuses staging and production
DEV-0023 | P01 | Identity administration frontend | Frontend | Feature | Complete | codex/backend-integration | a796a43 | Users, Roles & Permissions, Departments | Frontend Team | 2026-08-26 | Uniform lists, modals and floating row actions
DEV-0024 | P01 | Account and login experience | Frontend | Feature | Complete | codex/backend-integration | a796a43 | Login card and sidebar account menu | Frontend Team | 2026-08-26 | Session loading remains on login card; account menu floats
DEV-0025 | P01 | Excel transaction export | Frontend | Feature | Complete | codex/backend-integration | 44e876e | Export Excel + verified XLSX | Frontend Team | 2026-08-28 | Filtered Finance report reopened with correct sheets, rows, and total
DEV-0026 | P01 | Phase 01 validation and release | Delivery | Quality | Complete | codex/backend-integration | 44e876e | 28 tests / 90.59% / clean audits / release archive | Paolo Ylag | 2026-08-28 | Local release gates passed; external production-promotion checks recorded
DEV-0027 | P01 | Frontend-only synchronization | Frontend | Delivery | Complete | codex/frontend-only-prototype | 7043f0f | Standalone mock-mode build and route smoke test | Frontend Team | 2026-08-27 | Six reviewed assets synchronized without backend code

## Test Cases
Test Case Catalog
Master test definitions. Add a new execution row for every run; do not overwrite historical evidence.
Test ID | Phase | Feature | Test Type | Preconditions | Steps | Expected Result | Automation | Command / URL | Priority | Current Result | Acceptance Required | Evidence / Notes
TC-P00-001 | P00 | Process liveness | API | Compose stack running | GET /healthz | HTTP 200, status=ok, X-Request-ID present | Automated | pytest tests/test_system.py::test_liveness_returns_request_id | Critical | Passed | Yes | Local run 2026-08-25
TC-P00-002 | P00 | Database readiness | Integration | PostgreSQL healthy | GET /readyz | HTTP 200, status=ready, database=connected | Automated | pytest tests/test_system.py::test_readiness_requires_database | Critical | Passed | Yes | Local Docker run 2026-08-25
TC-P00-003 | P00 | API discovery | API | API running | GET /api | Version, environment, /api/v1 prefix and /docs returned | Automated | pytest tests/test_system.py::test_api_root_describes_versioned_api | High | Passed | Yes | Local run 2026-08-25
TC-P00-004 | P00 | System status | Integration | Database connected | GET /api/v1/system/status | Asia/Manila and database=connected | Automated | pytest tests/test_system.py::test_system_status_uses_philippine_timezone | Critical | Passed | Yes | Local Docker run 2026-08-25
TC-P00-005 | P00 | Problem response | Negative | API running | GET /missing | 404 application/problem+json with code and request_id | Automated | pytest tests/test_system.py::test_not_found_uses_problem_details | High | Passed | Yes | Local run 2026-08-25
TC-P00-006 | P00 | Request ID propagation | API | API running | Send X-Request-ID header | Response returns the supplied trace identifier | Manual | Invoke-WebRequest with X-Request-ID | Medium | Passed | No | Supplied phase-00-propagation-test returned unchanged
TC-P00-007 | P00 | CORS preflight | Security | Frontend origin configured | OPTIONS system status from 127.0.0.1:5175 | Allowed origin and methods returned | Manual | curl.exe OPTIONS /api/v1/system/status | High | Passed | Yes | Local run 2026-08-25
TC-P00-008 | P00 | PostgreSQL health | Infrastructure | Docker engine running | docker compose ps | app and db report healthy | Manual | docker compose ps | Critical | Passed | Yes | Local run 2026-08-25
TC-P00-009 | P00 | Migration applied | Database | Database initialized | Query alembic_version | Revision equals 20260819_0001 | Automated | alembic upgrade head | Critical | Passed | Yes | Local run 2026-08-25
TC-P00-010 | P00 | Migration rollback/replay | Database | Foundation-only dev data | downgrade base then upgrade head | Both operations succeed transactionally | Automated | alembic downgrade base; alembic upgrade head | Critical | Passed | Yes | Local run 2026-08-25
TC-P00-011 | P00 | Deterministic seed | Database | Migration applied | Run seed twice | Exactly four settings with expected values | Automated | pytest tests/test_seed.py | Critical | Passed | Yes | Local run 2026-08-25
TC-P00-012 | P00 | Database timezone | Database | Database connected | SHOW TIME ZONE | Asia/Manila | Automated | system status test plus SQL query | High | Passed | Yes | Local run 2026-08-25
TC-P00-013 | P00 | Backend lint | Static | Dev dependencies installed | Run Ruff | No lint violations | Automated | ruff check api migrations tests | High | Passed | Yes | Local run 2026-08-25
TC-P00-014 | P00 | Backend suite | Automated | PostgreSQL available | Run pytest with coverage | 6 tests pass; coverage reported | Automated | pytest --cov=payment_module | Critical | Passed | Yes | 6 passed; 89% coverage
TC-P00-015 | P00 | Frontend production build | Build | Node dependencies installed | Run pnpm build | TypeScript and Vite build succeed | Automated | pnpm build | Critical | Passed | Yes | Vite 7.0.7 build passed
TC-P00-016 | P00 | Hybrid API indicator | UI | Frontend and API running | Open dashboard | Dashboard renders and shows API connected | Manual | http://127.0.0.1:5175/#/dashboard | Critical | Passed | Yes | Browser verified; no console errors
TC-P00-017 | P00 | Mock fallback | Resilience | Frontend running | Stop API and reload hybrid frontend | Prototype remains usable with API unavailable indicator | Manual | docker compose stop app; reload | High | Passed | Yes | Dashboard remained usable and showed Hybrid · mock fallback
TC-P00-018 | P00 | Docker image build | Delivery | Docker engine running | Build API image | payment-module-app image produced | Automated | docker compose build | Critical | Passed | Yes | Local and CI packaging passed
TC-P00-019 | P00 | OpenAPI availability | API | API running | GET /docs and /openapi.json | Swagger UI and schema available | Manual | http://127.0.0.1:8002/docs | Medium | Passed | No | API docs route published
TC-P00-020 | P00 | Structured request logging | Operations | API running | Send request and inspect container log | Method, path, status, duration and request ID recorded | Manual | docker compose logs app | High | Passed | Yes | Log contained method, path, status, duration_ms and request_id
TC-P01-001 | P01 | Password hashing | Security | Test password available | Hash identical password twice; verify correct and incorrect passwords | Hashes differ; correct password verifies; incorrect password fails | Automated | pytest tests/test_identity.py::test_password_hash_is_salted_and_verifiable | Critical | Passed | Yes | Local run 2026-08-26
TC-P01-002 | P01 | Identity seed | Database | Migration head applied | Run identity seed twice | Reference identities remain deterministic with nine users and eight permissions | Automated | pytest tests/test_identity.py::test_phase_01_seed_is_deterministic | Critical | Passed | Yes | Local run 2026-08-26
TC-P01-003 | P01 | Login, session and logout | API | Seeded administrator | Login; read session; logout; read session again | Login and session return 200; logout revokes session; later read returns 401 | Automated | pytest tests/test_identity.py::test_login_session_logout_and_revocation | Critical | Passed | Yes | Local run 2026-08-26
TC-P01-004 | P01 | Invalid authentication | Negative | Seeded identities | Use invalid password and call protected endpoint without session | Invalid login and unauthenticated protected request return 401 | Automated | pytest tests/test_identity.py::test_invalid_login_and_unauthenticated_request_are_rejected | Critical | Passed | Yes | Local run 2026-08-26
TC-P01-005 | P01 | Role permission boundary | Authorization | Requestor identity | Read departments then attempt user administration | Granted read succeeds; unauthorized user list returns 403 | Automated | pytest tests/test_identity.py::test_role_permissions_and_explicit_deny_take_precedence | Critical | Passed | Yes | Local run 2026-08-26
TC-P01-006 | P01 | Audited department creation | Audit | Administrator session | Create department and inspect audit event | Department persists and creation event identifies the entity | Automated | pytest tests/test_identity.py::test_admin_can_add_department_and_change_is_audited | High | Passed | Yes | Local run 2026-08-26
TC-P01-007 | P01 | Idle and suspended account rejection | Security | Finance Associate identity | Age session past 60 minutes; suspend account; retry | Idle session and suspended account are rejected | Automated | pytest tests/test_identity.py::test_idle_session_and_suspended_user_are_rejected | Critical | Passed | Yes | Local run 2026-08-26
TC-P01-008 | P01 | Role assignment audit | Authorization | Administrator session | Replace requestor roles and inspect event | Role set is replaced and user.roles_changed is audited | Automated | pytest tests/test_identity.py::test_admin_can_replace_roles_and_change_is_audited | High | Passed | Yes | Local run 2026-08-26
TC-P01-009 | P01 | Explicit permission deny | Authorization | Requestor with department read grant | Apply deny override; re-login; read departments | Explicit deny overrides role permission and returns 403 | Automated | pytest tests/test_identity.py::test_explicit_permission_deny_overrides_role_grant | Critical | Passed | Yes | Local run 2026-08-26
TC-P01-010 | P01 | CSRF protection | Security | Authenticated administrator | POST department without CSRF token | Authenticated mutation is rejected with 403 | Automated | pytest tests/test_identity.py::test_csrf_is_required_for_authenticated_mutations | Critical | Passed | Yes | Local run 2026-08-26
TC-P01-011 | P01 | User suspension revokes sessions | Security | Administrator and temporary user | Create user; login; suspend; retry login | User creation succeeds; suspension revokes sessions and rejects login | Automated | pytest tests/test_identity.py::test_admin_can_create_and_suspend_user_with_session_revocation | Critical | Passed | Yes | Local run 2026-08-26
TC-P01-012 | P01 | Requestor-manager association | Identity | Manager and requestor users | Assign manager; attempt self-assignment and a cycle | Valid association persists; self and cyclic relationships return 422 | Automated | pytest tests/test_identity.py::test_admin_can_assign_requestor_manager_and_cycles_are_rejected | Critical | Passed | Yes | Local run 2026-08-26
TC-P01-013 | P01 | Administration CRUD safeguards | API | Administrator session | Create, edit and delete users, departments, roles and permissions | CRUD succeeds; referenced department deletion returns 409 until reassigned | Automated | pytest tests/test_identity.py::test_admin_crud_for_users_departments_roles_and_permissions | Critical | Passed | Yes | Local run 2026-08-26
TC-P01-014 | P01 | Session retention cleanup | Maintenance | Controlled active and invalid sessions | Dry run then clean in batches | Only invalid sessions older than 30 days are deleted; active/recent rows remain | Automated | pytest tests/test_maintenance.py::test_cleanup_deletes_only_sessions_past_retention | Critical | Passed | Yes | Local run 2026-08-26
TC-P01-015 | P01 | Cleanup environment refusal | Security | Cleanup explicitly enabled | Invoke cleanup with staging and production environments | Command hard-refuses both environments | Automated | pytest tests/test_maintenance.py::test_cleanup_is_refused_outside_local_and_test | Critical | Passed | Yes | Local production refusal verified
TC-P01-016 | P01 | Cleanup enablement guard | Security | Cleanup disabled | Invoke cleanup without enablement flag | Command refuses execution while disabled | Automated | pytest tests/test_maintenance.py::test_cleanup_must_be_explicitly_enabled | Critical | Passed | Yes | Local run 2026-08-26
TC-P01-017 | P01 | Test-session teardown isolation | Database | Development database session count recorded | Run login test; recount auth_sessions | Test-created sessions are removed and total count does not increase | Automated | pytest login test; compare auth_sessions count | High | Passed | Yes | Count remained 90 after repeated login test
TC-P01-018 | P01 | Identity migration rollback/replay | Database | PostgreSQL 16 available | Upgrade through 0004; downgrade; replay to head | Identity, manager and cleanup indexes migrate reversibly | Automated | alembic downgrade 20260825_0003; alembic upgrade head | Critical | Passed | Yes | Migration upgrade/downgrade/replay passed
TC-P01-019 | P01 | Backend quality gate | Quality | Development dependencies and PostgreSQL available | Run Ruff and full suite with coverage threshold | Ruff passes; 23 tests pass; coverage is at least 85% | Automated | ruff check api tests migrations; pytest --cov-fail-under=85 | Critical | Passed | Yes | 23 passed; 90.46% coverage
TC-P01-020 | P01 | Authenticated administration UI | UI | API, frontend and administrator session | Open Users, Roles & Permissions and Departments; exercise menus and add modals | Lists align; action popovers float; all four modals are contained | Manual | Browser walkthrough at http://127.0.0.1:5175 | High | Passed | Yes | Authenticated desktop audit passed
TC-P01-021 | P01 | Standalone frontend regression | Resilience | Frontend-only branch dependencies installed | Build and launch with VITE_DATA_SOURCE=mock; open four routes | Build succeeds; routes render Mock data with no horizontal overflow | Automated | pnpm build; VITE_DATA_SOURCE=mock vite --port 5177 | Critical | Passed | Yes | Frontend commit 7043f0f validated 2026-08-27
TC-P01-022 | P01 | Department report Excel export | UI | Dashboard report data available | Apply filters and select Export Excel | Browser downloads a valid XLSX report using active filters | Manual | Dashboard > Department Transaction Report > Export Excel | High | Passed | Yes | Finance-filtered XLSX reopened: Summary + Transactions, 2 rows, PHP 113,850
TC-P01-023 | P01 | Dedicated test database lifecycle | Database | Empty payment_module_test database | Upgrade 0001-0004; seed twice; downgrade to base; replay to head | All migration and deterministic seed operations complete on the isolated database | Automated | alembic upgrade/downgrade/replay using TEST_DATABASE_URL | Critical | Passed | Yes | Isolated PostgreSQL 16 validation 2026-08-27
TC-P01-024 | P01 | Concurrent login and session fixation | Security | Seeded administrator | Run four concurrent logins and supply an attacker-controlled cookie | Each login receives a distinct valid session; supplied cookie is replaced; HttpOnly/SameSite/Path flags are present | Automated | pytest tests/test_release_readiness.py | Critical | Passed | Yes | 3 release-readiness tests passed
TC-P01-025 | P01 | Concurrent-session suspension | Security | Two active requestor sessions and administrator | Suspend requestor while both sessions are active | Both sessions immediately return 401 and account can be safely restored | Automated | pytest test_suspension_revokes_all_concurrent_sessions | Critical | Passed | Yes | Isolated database; test state restored
TC-P01-026 | P01 | Large session cleanup batch | Maintenance | 2,005 expired sessions and one active session | Clean with batch size 500 | All 2,005 expired sessions are deleted across batches and active session remains | Automated | pytest test_cleanup_batches_thousands_without_removing_active_sessions | High | Passed | Yes | 27-test suite; cleanup data removed
TC-P01-027 | P01 | PostgreSQL backup and restore | Recovery | Migrated isolated database | pg_dump custom format; restore to fresh database; compare revision and table counts | Revision 20260826_0004 and sampled counts match exactly | Automated | pg_dump / pg_restore payment_module_test | Critical | Passed | Yes | Restore DB and dump removed after comparison
TC-P01-028 | P01 | Session continuity after API restart | Recovery | Disposable API container and authenticated test session | Restart API container; reuse session cookie | Session remains valid and returns 200 after restart | Automated | Disposable Docker API on port 8003 | Critical | Passed | Yes | Required rebuilding stale local image; disposable resources removed
TC-P01-029 | P01 | Python static security scan | Security | Current API source | Run Bandit recursively excluding tests | No low, medium or high findings | Automated | bandit -r api -x tests | High | Passed | Yes | 1,269 LOC scanned; zero findings
TC-P01-030 | P01 | Python dependency vulnerability audit | Security | Installed runtime and test environment | Audit installed packages against current vulnerability data | No known vulnerable runtime dependencies | Automated | pip-audit --local --skip-editable | Critical | Passed | Yes | pip-audit found no known vulnerabilities after runtime dependency remediation
TC-P01-031 | P01 | Frontend dependency vulnerability audit | Security | Current pnpm lockfile | Run pnpm audit | No high or moderate vulnerabilities | Automated | pnpm audit | Critical | Passed | Yes | pnpm audit found no known vulnerabilities; SheetJS 0.20.3 vendored from official distribution
TC-P01-032 | P01 | Integrated frontend production build | Frontend | Bundled Node runtime and installed dependencies | Run TypeScript and Vite production build | Build completes and emits HTML, CSS, application and XLSX chunks | Automated | pnpm run build | Critical | Passed | Yes | Vite build completed 2026-08-27
TC-P01-033 | P01 | Frontend/API proxy smoke test | Integration | Integrated frontend on 5176; API on 8002 | Load root; login and logout through Vite proxy | Root returns 200; proxy login succeeds; logout returns 204 | Automated | HTTP smoke test against 127.0.0.1:5176 | Critical | Passed | Yes | Frontend-only port 5175 was not used
TC-P01-034 | P01 | Responsive and accessibility walkthrough | UI | Interactive browser automation available | Test admin pages, modals, keyboard flow, labels and narrow layouts | No alignment, focus, naming or overflow defects | Manual | In-app browser walkthrough | High | Passed | Yes | Desktop/mobile administration walkthrough found no overflow, unnamed buttons, or unlabeled controls
TC-P01-035 | P01 | Cross-browser compatibility | UI | Chrome, Firefox and Safari environments | Run authentication and administration smoke paths in each browser | Supported browsers render and behave consistently | Manual | External browser matrix | High | Blocked | No | Chrome and in-app Chromium passed; Firefox and Safari unavailable on Windows host
TC-P01-036 | P01 | Downloaded Excel workbook integrity | Reporting | Interactive browser download available | Export filtered department report; reopen workbook and validate sheets/filters | Valid XLSX contains Summary and Transactions sheets matching active filters | Manual | Dashboard > Export Excel > reopen workbook | High | Passed | Yes | Downloaded workbook sheets, filters, totals, and formula-error scan passed

## Test Executions
Test Execution History
Append-only history of test runs, actual results, defects and retest requirements.
Run ID | Test ID | Run Date | Environment | Build / Commit | Execution Status | Result | Actual Result | Executed By | Defect ID | Retest | Notes
RUN-20260825-001 | TC-P00-001 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-002 | TC-P00-002 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local Docker run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-003 | TC-P00-003 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-004 | TC-P00-004 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local Docker run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-005 | TC-P00-005 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-006 | TC-P00-006 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Supplied phase-00-propagation-test returned unchanged | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-007 | TC-P00-007 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-008 | TC-P00-008 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-009 | TC-P00-009 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-010 | TC-P00-010 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-011 | TC-P00-011 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-012 | TC-P00-012 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-013 | TC-P00-013 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-014 | TC-P00-014 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | 6 passed; 89% coverage | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-015 | TC-P00-015 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Vite 7.0.7 build passed | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-016 | TC-P00-016 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Browser verified; no console errors | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-017 | TC-P00-017 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Dashboard remained usable and showed Hybrid · mock fallback | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-018 | TC-P00-018 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local and CI packaging passed | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-019 | TC-P00-019 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | API docs route published | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-020 | TC-P00-020 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Log contained method, path, status, duration_ms and request_id | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260826-021 | TC-P01-001 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-022 | TC-P01-002 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-023 | TC-P01-003 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-024 | TC-P01-004 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-025 | TC-P01-005 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-026 | TC-P01-006 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-027 | TC-P01-007 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-028 | TC-P01-008 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-029 | TC-P01-009 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-030 | TC-P01-010 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-031 | TC-P01-011 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-032 | TC-P01-012 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-033 | TC-P01-013 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-034 | TC-P01-014 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-035 | TC-P01-015 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local production refusal verified | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-036 | TC-P01-016 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Local run 2026-08-26 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-037 | TC-P01-017 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Count remained 90 after repeated login test | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-038 | TC-P01-018 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Migration upgrade/downgrade/replay passed | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-039 | TC-P01-019 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | 23 passed; 90.46% coverage | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-040 | TC-P01-020 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Executed | Passed | Authenticated desktop audit passed | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-041 | TC-P01-021 | 2026-08-26 | Frontend-only mock / Vite 7.0.7 | 7043f0f | Executed | Passed | Frontend commit 7043f0f validated 2026-08-27 | Codex local audit |  | No | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260826-042 | TC-P01-022 | 2026-08-26 | Local Windows / Docker Desktop / PostgreSQL 16 | a796a43 | Blocked | Blocked | XLSX export implementation and build passed | Codex local audit |  | Required | Evidence recorded in docs/phase-01-plan.md and PROJECT_MANIFEST.md
RUN-20260827-001 | TC-P01-023 | 2026-08-27 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7 | working tree after acb887f | Executed | Passed | Isolated PostgreSQL 16 validation 2026-08-27 | Codex local release-readiness audit |  | No | Isolated PostgreSQL 16 validation 2026-08-27
RUN-20260827-002 | TC-P01-024 | 2026-08-27 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7 | working tree after acb887f | Executed | Passed | 3 release-readiness tests passed | Codex local release-readiness audit |  | No | 3 release-readiness tests passed
RUN-20260827-003 | TC-P01-025 | 2026-08-27 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7 | working tree after acb887f | Executed | Passed | Isolated database; test state restored | Codex local release-readiness audit |  | No | Isolated database; test state restored
RUN-20260827-004 | TC-P01-026 | 2026-08-27 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7 | working tree after acb887f | Executed | Passed | 27-test suite; cleanup data removed | Codex local release-readiness audit |  | No | 27-test suite; cleanup data removed
RUN-20260827-005 | TC-P01-027 | 2026-08-27 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7 | working tree after acb887f | Executed | Passed | Restore DB and dump removed after comparison | Codex local release-readiness audit |  | No | Restore DB and dump removed after comparison
RUN-20260827-006 | TC-P01-028 | 2026-08-27 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7 | working tree after acb887f | Executed | Passed | Required rebuilding stale local image; disposable resources removed | Codex local release-readiness audit |  | No | Required rebuilding stale local image; disposable resources removed
RUN-20260827-007 | TC-P01-029 | 2026-08-27 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7 | working tree after acb887f | Executed | Passed | 1,269 LOC scanned; zero findings | Codex local release-readiness audit |  | No | 1,269 LOC scanned; zero findings
RUN-20260827-008 | TC-P01-030 | 2026-08-27 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7 | working tree after acb887f | Executed | Failed | Runtime findings include python-multipart 0.0.20 and Starlette 0.47.3; dev tooling also reported | Codex local release-readiness audit | Dependency remediation required | Required | Runtime findings include python-multipart 0.0.20 and Starlette 0.47.3; dev tooling also reported
RUN-20260827-009 | TC-P01-031 | 2026-08-27 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7 | working tree after acb887f | Executed | Failed | 9 advisories: 5 high and 4 moderate; includes xlsx, Vite, nanoid and postcss | Codex local release-readiness audit | Dependency remediation required | Required | 9 advisories: 5 high and 4 moderate; includes xlsx, Vite, nanoid and postcss
RUN-20260827-010 | TC-P01-032 | 2026-08-27 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7 | working tree after acb887f | Executed | Passed | Vite build completed 2026-08-27 | Codex local release-readiness audit |  | No | Vite build completed 2026-08-27
RUN-20260827-011 | TC-P01-033 | 2026-08-27 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7 | working tree after acb887f | Executed | Passed | Frontend-only port 5175 was not used | Codex local release-readiness audit |  | No | Frontend-only port 5175 was not used
RUN-20260827-012 | TC-P01-034 | 2026-08-27 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7 | working tree after acb887f | Blocked | Blocked | Browser automation runtime failed to load; requires rerun in an interactive browser | Codex local release-readiness audit |  | No | Browser automation runtime failed to load; requires rerun in an interactive browser
RUN-20260827-013 | TC-P01-035 | 2026-08-27 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7 | working tree after acb887f | Blocked | Blocked | Only local Chromium surface is available; Firefox and Safari were not executed | Codex local release-readiness audit |  | No | Only local Chromium surface is available; Firefox and Safari were not executed
RUN-20260827-014 | TC-P01-036 | 2026-08-27 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7 | working tree after acb887f | Blocked | Blocked | Implementation and build pass, but an actual browser download was not captured | Codex local release-readiness audit |  | No | Implementation and build pass, but an actual browser download was not captured
RUN-20260828-001 | TC-P01-022 | 2026-08-28 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7.3.6 / Chrome | 44e876e | Executed | Passed | Finance filter downloaded a valid XLSX: Summary + Transactions, 2 rows, PHP 113,850 | Codex final Phase 01 validation
RUN-20260828-002 | TC-P01-030 | 2026-08-28 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7.3.6 / Chrome | 44e876e | Executed | Passed | pip-audit: no known vulnerabilities after dependency remediation | Codex final Phase 01 validation
RUN-20260828-003 | TC-P01-031 | 2026-08-28 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7.3.6 / Chrome | 44e876e | Executed | Passed | pnpm audit: no known vulnerabilities; official SheetJS 0.20.3 package vendored | Codex final Phase 01 validation
RUN-20260828-004 | TC-P01-034 | 2026-08-28 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7.3.6 / Chrome | 44e876e | Executed | Passed | In-app browser desktop/mobile admin walkthrough passed naming, labels, modal containment, and overflow checks | Codex final Phase 01 validation
RUN-20260828-005 | TC-P01-035 | 2026-08-28 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7.3.6 / Chrome | 44e876e | Executed | Blocked | Desktop Chrome and in-app Chromium passed; Firefox and Safari unavailable on this Windows host | Codex final Phase 01 validation | Accepted limitation; execute before production promotion
RUN-20260828-006 | TC-P01-036 | 2026-08-28 | Windows / Docker Desktop / PostgreSQL 16 / Vite 7.3.6 / Chrome | 44e876e | Executed | Passed | Downloaded workbook reopened successfully; filters, totals, sheets, and formula-error scan passed | Codex final Phase 01 validation

## Acceptance Matrix
Acceptance Matrix
Phase gates mapped to test IDs and objective evidence. A gate remains pending until every required linked test passes.
Gate ID | Phase | Gate | Acceptance Requirement | Linked Tests | Required | Result | Evidence / Limitation | Accepted Date | Accepted By
AG-P00-01 | P00 | API foundation | Liveness, readiness, discovery, versioned system route and docs are available | TC-P00-001, TC-P00-002, TC-P00-003, TC-P00-004, TC-P00-019 | Yes | Accepted | Validated locally and in CI | 2026-08-25 | Paolo Ylag
AG-P00-02 | P00 | Database foundation | PostgreSQL, migration, seed and Asia/Manila session operate repeatably | TC-P00-008, TC-P00-009, TC-P00-010, TC-P00-011, TC-P00-012 | Yes | Accepted | Validated against local PostgreSQL 16 | 2026-08-25 | Paolo Ylag
AG-P00-03 | P00 | API standards | Problem responses, request IDs, CORS and logging conventions are established | TC-P00-005, TC-P00-006, TC-P00-007, TC-P00-020 | Yes | Accepted | Request propagation, CORS and structured log fields verified | 2026-08-25 | Paolo Ylag
AG-P00-04 | P00 | Automated quality | Lint, tests, coverage and production build pass | TC-P00-013, TC-P00-014, TC-P00-015 | Yes | Accepted | 6 tests passed; 89% coverage; Vite build passed | 2026-08-25 | Paolo Ylag
AG-P00-05 | P00 | Delivery packaging | Docker image builds and both Compose services become healthy | TC-P00-008, TC-P00-018 | Yes | Accepted | Local Docker and GitHub package job passed | 2026-08-25 | Paolo Ylag
AG-P00-06 | P00 | Continuously runnable prototype | Hybrid frontend connects to API and falls back safely when API is unavailable | TC-P00-016, TC-P00-017 | Yes | Accepted | API connected and Hybrid · mock fallback states both verified | 2026-08-25 | Paolo Ylag
AG-P01-01 | P01 | Identity persistence | Identity records and deterministic seed migrate repeatably | TC-P01-002, TC-P01-018 | Yes | Accepted | Identity migrations and deterministic seed passed | 2026-08-26 | Paolo Ylag
AG-P01-02 | P01 | Authentication and sessions | Local login, CSRF, logout, idle expiry and revocation are enforced | TC-P01-001, TC-P01-003, TC-P01-004, TC-P01-007, TC-P01-010, TC-P01-011 | Yes | Accepted | Authentication and session security tests passed | 2026-08-26 | Paolo Ylag
AG-P01-03 | P01 | RBAC boundaries | Role grants, explicit denies and audited assignments are authoritative | TC-P01-005, TC-P01-008, TC-P01-009 | Yes | Accepted | Permission boundaries and deny precedence passed | 2026-08-26 | Paolo Ylag
AG-P01-04 | P01 | Administration and associations | Users, departments, roles, permissions and manager links are safely administered | TC-P01-006, TC-P01-012, TC-P01-013 | Yes | Accepted | CRUD safeguards, audit records and cycle rejection passed | 2026-08-26 | Paolo Ylag
AG-P01-05 | P01 | Session hygiene | Tests do not accumulate sessions and retained cleanup cannot reach production | TC-P01-014, TC-P01-015, TC-P01-016, TC-P01-017 | Yes | Accepted | Retention, teardown, disablement and production refusal passed | 2026-08-26 | Paolo Ylag
AG-P01-06 | P01 | Administration frontend | Identity pages use uniform lists, menus, modals and responsive containment | TC-P01-020 | Yes | Accepted | Authenticated administration walkthrough passed | 2026-08-26 | Paolo Ylag
AG-P01-07 | P01 | Standalone frontend | Frontend-only mock mode remains runnable and report export builds | TC-P01-021, TC-P01-022 | Yes | Accepted | Standalone mock mode and real filtered Excel export passed | 2026-08-28 | Paolo Ylag
AG-P01-08 | P01 | Automated quality and release | Lint, coverage, migrations and reviewed release package pass | TC-P01-018, TC-P01-019 | Yes | Accepted | 28 tests, 90.59% coverage, clean dependency audits, build, package, and local browser checks passed | 2026-08-28 | Paolo Ylag

## Instructions
Workbook Maintenance Guide
Use this workbook as the QA system of record for development phases and repeatable acceptance decisions.
Step | When | Action | Sheet | Required Fields | Rule
1 | A work item starts | Add or update its development row | Development Log | Phase, work item, status, branch, owner | Do not mark Complete without evidence
2 | A requirement is testable | Create a stable test ID | Test Cases | Steps, expected result, priority, acceptance flag | Never recycle test IDs
3 | A test is executed | Append a new run | Test Executions | Run ID, date, build, result, evidence | Never overwrite historical runs
4 | A defect is found | Record the defect and retest requirement | Test Executions | Defect ID, result, retest | Failed acceptance tests block the gate
5 | A gate is reviewed | Confirm linked required tests | Acceptance Matrix | Result, evidence, accepted date/by | Pending if any required test is not passed
6 | A phase is approved | Update the phase ledger | Phase Register | Status, validation reference, date | Use Validated only after acceptance review
7 | A release/build changes | Create fresh execution rows | Test Executions | New build/commit and actual result | Re-run affected regression tests
Controlled field | Allowed values
Phase Status | Not Started; In Progress; Ready for Validation; Validated; Blocked
Test Result | Not Run; Passed; Failed; Blocked; N/A
Priority | Critical; High; Medium; Low
Acceptance Result | Pending; Accepted; Rejected; Blocked
Retest | No; Required; Completed
Evidence | Command output, URL, CI run, screenshot, log, commit or document reference