## Dashboard
Automated Payment System — Development & QA Dashboard
Live register for delivery phases, test execution, acceptance gates and evidence. Update source sheets; dashboard formulas recalculate.
Metric | Current | Phase 00 acceptance snapshot
Validated phases | 5 | AG-P00-01 | API foundation | Accepted | Validated locally and in CI | 2026-08-25
Total phases | 10 | AG-P00-02 | Database foundation | Accepted | Validated against local PostgreSQL 16 | 2026-08-25
Passed tests | 76 | AG-P00-03 | API standards | Accepted | Request propagation, CORS and structured log fields verified | 2026-08-25
Failed tests | 0 | AG-P00-04 | Automated quality | Accepted | 6 tests passed; 89% coverage; Vite build passed | 2026-08-25
Not-run tests | 1 | AG-P00-05 | Delivery packaging | Accepted | Local Docker and GitHub package job passed | 2026-08-25
|  | AG-P00-06 | Continuously runnable prototype | Accepted | API connected and Hybrid · mock fallback states both verified | 2026-08-25
|  | Test result | Count
|  | Passed | 76
|  | Failed | 0
|  | Not Run | 1
Current environment
|  | Branch | codex/backend-integration | Build | Phase 01-04 local closeout
|  | Frontend | http://127.0.0.1:5175/#/login | Status | API connected
|  | API | http://127.0.0.1:58002 | Status | Healthy
|  | Database | PostgreSQL 16 on 127.0.0.1:55434 | Migration | 20260930_0010
|  | Evidence | docs/phase-01-plan.md; docs/phase-02-validation.md; docs/phase-03-validation.md; docs/phase-04-validation.md | Updated | 2026-09-28 | 2026-10-07

## Phase Register
Phase Register
Status and acceptance boundary for every planned implementation phase.
Phase ID | Phase | Scope Summary | Status | Acceptance Gate | Validation Reference | Last Validated | Owner | Notes
P00 | Foundation | API foundation, PostgreSQL, migrations, seed, middleware, CI/CD and hybrid frontend status | Validated | All foundation gates pass locally and in CI | docs/phase-00-validation.md | 2026-09-23 | Backend Team | Validated; current Docker image, migration replay, health checks and logical restore passed on 2026-09-23.
P01 | Authentication and RBAC | Local auth, sessions, users, roles, permissions and authorization | Validated | Protected endpoints enforce identity, role and department boundaries | docs/phase-01-plan.md | 2026-10-07 | Backend Team | Validated locally; current five-role browser walkthrough, 99-test backend regression, migration replay, lint, dependency audits and production build passed on 2026-10-07. Production security and hosted accessibility remain Phase 09 gates.
P02 | Master Data | Departments, cost centers, vendors, accounts, tax codes, currencies and payment methods | Validated | Reference data is persisted, validated and safely administered | docs/phase-02-plan.md | 2026-10-07 | Backend Team | Validated for local development; all seven Master Data views, role controls and configuration forms passed browser and automated checks. Authoritative Finance reference data and live Procurement vendor activation remain accepted external limitations.
P03 | Payment Requests | Drafts, request types, numbering, line items, allocations, submission and locking | Validated | Every request type persists and enforces ownership and totals | docs/phase-03-validation.md | 2026-10-07 | Backend Team | Validated for local development; 99 backend tests, migration replay, five-role request lifecycle, Finance settings and current-device responsive suites passed. Live Procurement activation and deferred cash-out exception workflows remain accepted limitations.
P04 | Documents | Private files, metadata, checksum, replacement, rules, preview and review | Validated | Protected document lifecycle works against persisted requests | docs/phase-04-validation.md | 2026-10-07 | Backend Team | Validated for local development; private MinIO lifecycle, document requirements, five-role document workflow and per-line Reimbursement evidence passed. Production S3, scanning and retention remain Phase 09 gates.
P05 | Workflow and Approvals | Routes, assignments, queues, decisions, delegation, rerouting and immutable events | In Progress — Preview Only | Backend state machine rejects invalid or duplicate transitions | docs/phase-05-plan.md | 2026-10-07 | Backend Team | Read-only provisional route preview is implemented. Approver assignment and approval decisions are not persisted.
P06 | Finance and Vouchers | VAT/EWT, accounting entries, validation, voucher snapshots and certification | Not Started | Balanced entries and approved persisted vouchers are enforced | PROJECT_MANIFEST.md |  | Backend Team | Financial calculations require boundary tests
P07 | Payment Execution | Payment attempts, authorization, processing, release, retries, voids and replacements | Not Started | Segregation of duties and immutable payment history pass | PROJECT_MANIFEST.md |  | Backend Team | Support partial and multiple attempts
P08 | Notifications and Reporting | Outbox, delivery history, dashboards, tracker, aging, exports and reports | Not Started | Durable notifications and reconciled report totals pass | PROJECT_MANIFEST.md |  | Backend Team | Development mailbox before production email
P09 | Administration and Integrations | Policies, retention, monitoring, SAML, storage, ERP, banking and webhooks | Not Started | Adapters are replaceable, monitored and safely configurable | PROJECT_MANIFEST.md |  | Backend Team | Production ownership decisions required

## Development Log
Development Log
Implemented work and planned development items, linked to branch, build and evidence.
Dev ID | Phase | Work Item | Area | Type | Status | Branch | Commit | Evidence | Owner | Updated | Notes
DEV-0001 | P00 | Versioned API routing | FastAPI | Feature | Complete | codex/backend-integration | 4ddd199 | /api and /api/v1/system/status | Backend Team | 2026-08-25 | API discovery and versioned system route
DEV-0002 | P00 | Liveness and readiness | Operations | Feature | Complete | codex/backend-integration | 4ddd199 | /healthz and /readyz | Backend Team | 2026-08-25 | Readiness checks PostgreSQL independently
DEV-0003 | P00 | PostgreSQL 16 Compose service | Database | Infrastructure | Complete | codex/backend-integration | 4ddd199 | docker-compose.yml | Backend Team | 2026-08-25 | Persistent local volume and health check
DEV-0004 | P00 | SQLAlchemy and Psycopg foundation | Database | Feature | Complete | codex/backend-integration | 4ddd199 | api/payment_module/database.py | Backend Team | 2026-08-25 | Session and rollback conventions
DEV-0005 | P00 | Alembic foundation migration | Database | Migration | Complete | codex/backend-integration | 4ddd199 | 20260819_0001 | Backend Team | 2026-08-25 | Creates plural system_settings table
DEV-0006 | P00 | Deterministic seed | Database | Feature | Complete | codex/backend-integration | 4ddd199 | python -m payment_module.seed | Backend Team | 2026-08-25 | Four idempotent system settings
DEV-0007 | P00 | Problem responses | API | Middleware | Complete | codex/backend-integration | 4ddd199 | application/problem+json | Backend Team | 2026-08-25 | Standardized 404 and request ID
DEV-0008 | P00 | Correlation IDs and logging | Operations | Middleware | Complete | codex/backend-integration | 4ddd199 | X-Request-ID | Backend Team | 2026-08-25 | Structured request logs
DEV-0009 | P00 | CORS configuration | Security | Middleware | Complete | codex/backend-integration | 4ddd199 | Origin http://127.0.0.1:5175 | Backend Team | 2026-08-25 | Configurable comma-separated origins
DEV-0010 | P00 | Philippine timezone | Platform | Convention | Complete | codex/backend-integration | 4ddd199 | Asia/Manila | Backend Team | 2026-08-25 | API and database session aligned
DEV-0011 | P00 | Hybrid frontend adapter | Frontend | Feature | Complete | codex/backend-integration | 4ddd199 | API connected indicator | Frontend Team | 2026-08-25 | Mock, hybrid and API modes
DEV-0012 | P00 | Backend CI and packaging | Delivery | CI/CD | Complete | codex/backend-integration | 4ddd199 | GitHub run 32719293106 | Backend Team | 2026-08-24 | Test and package jobs successful
DEV-0013 | P00 | Local Docker validation | Delivery | Environment | Complete | codex/backend-integration | 4ddd199 | Docker 29.6.2 / WSL 2.7.12 | Paolo Ylag | 2026-08-25 | PostgreSQL and API containers healthy
DEV-0014 | P03 | Concurrent request safety and bounded pagination | Payment Requests | Reliability | Complete | codex/backend-integration | f9555f2 + concurrency test changes | api/payment_module/routers/requests.py; tests/test_payment_requests.py | Backend Team | 46285 | Row/advisory locks, idempotency recheck, 100-row page cap and batched serialization
DEV-0015 | P03 | Server-side request search, filters and stable sorting | Payment Requests | Feature | Complete | codex/backend-integration | working tree after 1752be2 | api/payment_module/routers/requests.py; src/data-source.js; src/prototype.js | Backend Team | 46286 | Role-scoped pagination and API-backed frontend filters
DEV-0016 | P03 | Audited 90-day draft archival | Operations | Retention | Complete | codex/backend-integration | working tree after 1752be2 | api/payment_module/maintenance.py; tests/test_maintenance.py | Backend Team | 46286 | Explicitly enabled, batched, dry-run capable and does not delete submitted records
DEV-0017 | P03 | Request authorization and monetary boundary hardening | Security | Test | Complete | codex/backend-integration | working tree after 1752be2 | tests/test_payment_requests.py | Backend Team | 46286 | Manager scope, explicit deny, privileged-read audit and PHP/USD/EUR boundaries
DEV-0018 | P03 | Phase 03 request API documentation | Documentation | Documentation | Complete | codex/backend-integration | working tree after 1752be2 | docs/phase-03-api.md | Backend Team | 46286 | Documents query parameters, lifecycle, validation, retention and error behavior
DEV-0019 | P04 | Document metadata, version and link persistence | Documents | Feature | Complete | codex/backend-integration | current working tree | models/documents.py; migration 20260923_0008 | Backend Team | 46288 | Private document metadata, immutable versions and request/line links persisted
DEV-0020 | P04 | S3-compatible storage and local MinIO | Documents | Feature | Complete | codex/backend-integration | current working tree | document storage service; docker-compose.yml | Backend Team | 46288 | Private versioned MinIO bucket validates the AWS S3-compatible contract locally
DEV-0021 | P04 | Configurable required-document evaluation | Documents | Feature | Complete | codex/backend-integration | current working tree | document_requirement_rules; submission validation | Backend Team | 46288 | Request- and line-level rules remain non-blocking until configured
DEV-0023 | P04 | Document frontend API integration | Frontend | Feature | Complete | codex/backend-integration | current working tree | src/data-source.js; src/prototype.js | Frontend Team | 46288 | Upload, preview, replace, remove, duplicate warnings and Finance controls; sample fallback retained
DEV-0024 | P04 | Phase 04 second-slice documentation | Documentation | Documentation | Complete | codex/backend-integration | current working tree | docs/phase-04-api.md; docs/phase-04-validation.md | Backend Team | 46288 | Implemented scope and production gates documented
DEV-0025 | P03 | Procurement-backed P.O. submission validation and snapshots | Payment Requests | Feature | Complete | codex/backend-integration | current working tree | procurement_adapter.py; routers/requests.py | Backend Team | 46290 | Backend independently verifies eligibility, amount, currency, vendor and duplicate use; safe vendor/P.O. facts are frozen at submission
DEV-0026 | P03 | Confirmed Cash Advance submission controls | Payment Requests | Feature | Complete | codex/backend-integration | current working tree | routers/requests.py; tests/test_payment_requests.py | Backend Team | 46290 | PHP 40,000 cap, exact 15-day liquidation due date and one outstanding advance per requestor are enforced transactionally
DEV-0027 | P03 | Finance timing and petty-cash guidance | Frontend | Feature | Complete | codex/backend-integration | current working tree | src/prototype.js | Frontend Team | 46290 | Reimbursement form displays nonblocking 15-day lead time, 30-day invoice, PHP 3,000 petty-cash and 15th/30th batch guidance
DEV-0028 | P03/P04 | Current local regression and validation records | Quality | Documentation | Complete | codex/backend-integration | current working tree | docs/phase-03-validation.md; docs/phase-04-validation.md; QA register | Backend Team | 46290 | Focused 30-test request suite, complete 72-test Docker/PostgreSQL regression, frontend build and healthy rebuilt API recorded
DEV-0029 | P03 | Procurement reference-data initial load correction | Frontend | Defect Fix | Complete | codex/backend-integration | current working tree | src/prototype.js | Frontend Team | 46290 | Not-loaded Procurement state is distinct from standalone fallback so API-connected request forms always fetch current eligible P.O. records
DEV-0030 | P03/P04 | Confirmed General Payment document requirements | Payment Requests | Business Rule | Complete | codex/backend-integration | current working tree | routers/requests.py; routers/documents.py; src/prototype.js | Backend Team | 46290 | Billing / SOA / Quotation is always required; BIR 2303 dynamically becomes blocking when the requestor marks a new supplier
DEV-0031 | P02/P03/P04 | Responsive layout and content-density audit | Frontend | UX | Complete | codex/backend-integration | cross-phase closeout | src/prototype.js; src/boilerplate-shell.css; src/styles.css | Frontend Team | 46293 | Responsive tables, disclosures, administration navigation and compact mobile layouts verified across supported routes
DEV-0032 | P03/P04 | Unified accessible file-upload controls | Frontend | UX | Complete | codex/backend-integration | cross-phase closeout | src/prototype.js; src/App.jsx; src/styles.css | Frontend Team | 46293 | Single, multiple, request-level, line-level, add and replace uploads share the line-item icon pattern
DEV-0033 | P00/P01/P02/P03/P04 | Cross-phase repository validation and records reconciliation | Quality | Validation | Complete | codex/backend-integration | cross-phase closeout | phase validation records; QA register | Backend Team | 46293 | Frontend build, 73-test Docker regression and five-role Chrome lifecycle passed; Ruff awaits the hosted CI package environment
DEV-0034 | P04 | Per-line Reimbursement Proof of Payment closeout | Documents | Validation | Complete | codex/backend-integration | current working tree | src/data-source.js; tests/e2e/phase-04-documents.spec.js; docs/phase-04-validation.md | Backend Team | 2026-09-29 | Mock and API rules now require Reimbursement support per line only; API-backed Chrome acceptance proves separate Proof of Payment uploads for both lines, no legacy request-level Invoice/Billing rule, and successful submission
DEV-0035 | P01/P02/P03/P04 | Local-development phase closeout and evidence reconciliation | Quality | Validation | Complete | codex/backend-integration | current closeout commit | PROJECT_MANIFEST.md; phase validation records; QA register | Backend Team | 46302 | Browser-first five-role and administration walkthrough passed after synchronizing the idempotent development seed. Lint, migration base/head replay, deterministic seed, 99 backend tests at 90% coverage, six headed Chrome suites, dependency audits and production build passed.

## Test Cases
Test Case Catalog
Master test definitions. Add a new execution row for every run; do not overwrite historical evidence.
Test ID | Phase | Feature | Test Type | Preconditions | Steps | Expected Result | Automation | Command / URL | Priority | Current Result | Acceptance Required | Evidence / Notes
TC-P00-001 | P00 | Process liveness | API | Compose stack running | GET /healthz | HTTP 200, status=ok, X-Request-ID present | Automated | pytest tests/test_system.py::test_liveness_returns_request_id | Critical | Passed | Yes | Local run 2026-08-25
TC-P00-002 | P00 | Database readiness | Integration | PostgreSQL healthy | GET /readyz | HTTP 200, status=ready, database=connected | Automated | pytest tests/test_system.py::test_readiness_requires_database | Critical | Passed | Yes | Local Docker run 2026-08-25
TC-P00-003 | P00 | API discovery | API | API running | GET /api | Version, environment, /api/v1 prefix and /docs returned | Automated | pytest tests/test_system.py::test_api_root_describes_versioned_api | High | Passed | Yes | Local run 2026-08-25
TC-P00-004 | P00 | System status | Integration | Database connected | GET /api/v1/system/status | Asia/Manila and database=connected | Automated | pytest tests/test_system.py::test_system_status_uses_philippine_timezone | Critical | Passed | Yes | Local Docker run 2026-08-25
TC-P00-005 | P00 | Problem response | Negative | API running | GET /missing | 404 application/problem+json with code and request_id | Automated | pytest tests/test_system.py::test_not_found_uses_problem_details | High | Passed | Yes | Local run 2026-08-25
TC-P00-006 | P00 | Request ID propagation | API | API running | Send X-Request-ID header | Response returns the supplied trace identifier | Manual | Invoke-WebRequest with X-Request-ID | Medium | Passed | No | Supplied phase-00-propagation-test returned unchanged
TC-P00-007 | P00 | CORS preflight | Security | Frontend origin configured | OPTIONS system status from 127.0.0.1:5175 | Allowed origin and methods returned | Manual | curl.exe OPTIONS /api/v1/system/status | High | Passed | Yes | Local run 2026-08-25
TC-P00-008 | P00 | PostgreSQL health | Infrastructure | Docker engine running | docker compose ps | app and db report healthy | Manual | docker compose ps | Critical | Passed | Yes | Local run 2026-08-25
TC-P00-009 | P00 | Migration applied | Database | Database initialized | Query alembic_version | Revision equals 20260819_0001 | Automated | alembic upgrade head | Critical | Passed | Yes | Local run 2026-08-25
TC-P00-010 | P00 | Migration rollback/replay | Database | Foundation-only dev data | downgrade base then upgrade head | Both operations succeed transactionally | Automated | alembic downgrade base; alembic upgrade head | Critical | Passed | Yes | Local run 2026-08-25
TC-P00-011 | P00 | Deterministic seed | Database | Migration applied | Run seed twice | Exactly four settings with expected values | Automated | pytest tests/test_seed.py | Critical | Passed | Yes | Local run 2026-08-25
TC-P00-012 | P00 | Database timezone | Database | Database connected | SHOW TIME ZONE | Asia/Manila | Automated | system status test plus SQL query | High | Passed | Yes | Local run 2026-08-25
TC-P00-013 | P00 | Backend lint | Static | Dev dependencies installed | Run Ruff | No lint violations | Automated | ruff check api migrations tests | High | Passed | Yes | Local run 2026-08-25
TC-P00-014 | P00 | Backend suite | Automated | PostgreSQL available | Run pytest with coverage | 6 tests pass; coverage reported | Automated | pytest --cov=payment_module | Critical | Passed | Yes | 6 passed; 89% coverage
TC-P00-015 | P00 | Frontend production build | Build | Node dependencies installed | Run pnpm build | TypeScript and Vite build succeed | Automated | pnpm build | Critical | Passed | Yes | Vite 7.0.7 build passed
TC-P00-016 | P00 | Hybrid API indicator | UI | Frontend and API running | Open dashboard | Dashboard renders and shows API connected | Manual | http://127.0.0.1:5175/#/dashboard | Critical | Passed | Yes | Browser verified; no console errors
TC-P00-017 | P00 | Mock fallback | Resilience | Frontend running | Stop API and reload hybrid frontend | Prototype remains usable with API unavailable indicator | Manual | docker compose stop app; reload | High | Passed | Yes | Dashboard remained usable and showed Hybrid · mock fallback
TC-P00-018 | P00 | Docker image build | Delivery | Docker engine running | Build API image | payment-module-app image produced | Automated | docker compose build | Critical | Passed | Yes | Local and CI packaging passed
TC-P00-019 | P00 | OpenAPI availability | API | API running | GET /docs and /openapi.json | Swagger UI and schema available | Manual | http://127.0.0.1:8002/docs | Medium | Passed | No | API docs route published
TC-P00-020 | P00 | Structured request logging | Operations | API running | Send request and inspect container log | Method, path, status, duration and request ID recorded | Manual | docker compose logs app | High | Passed | Yes | Log contained method, path, status, duration_ms and request_id
TC-P00-021 | P00 | Current Docker migration and seed replay | Integration | Isolated Docker PostgreSQL 16 databases | Upgrade base to head, downgrade to base, upgrade to head, then seed twice | Migration chain and deterministic seed complete without drift | Manual | alembic upgrade/downgrade; python -m payment_module.seed | Critical | Passed | Yes | Docker Desktop 4.92.0 / Engine 29.8.0; current head 20260922_0007
TC-P00-022 | P00 | PostgreSQL logical backup and restore | Recovery | Migrated and seeded disposable Docker database | Create custom-format dump, restore to a new database, compare schema and sampled counts | Revision, table count and sampled data counts match | Manual | pg_dump -Fc; pg_restore | Critical | Passed | Yes | Exact match: 23 tables, revision 20260922_0007, users/departments/cost centers/currencies/payment requests
TC-P01-001 | P01 | Live session restart continuity | Integration | Current app image and seeded Docker database | Login, read session, restart app container, read session, logout | Session survives app restart and is rejected after logout | Manual | Live API on isolated loopback port | Critical | Passed | Yes | Authenticated admin session survived restart; logout returned 204 and next session read returned 401
TC-P02-001 | P02 | Historical bank-table removal guard | Migration | Disposable database at 20260908_0006 with one synthetic historical row | Upgrade to head, verify refusal, remove fixture, upgrade again | Populated table is preserved; empty table is removed by 20260922_0007 | Manual | alembic upgrade head against phase02_guard_test | Critical | Passed | Yes | Guard preserved revision and row; clean retry removed table; no bank routes remain
TC-P03-001 | P03 | Request draft CRUD | API | Test database migrated and seeded | Create and retrieve an owned request draft | Draft persists with request, line, amount and currency | Automated | pytest tests/test_payment_requests.py | Critical | Passed | Yes | Local isolated PostgreSQL run 2026-09-08
TC-P03-002 | P03 | Single-currency enforcement | Negative | PHP request with USD line | POST /api/v1/requests | HTTP 422; mixed currency is rejected | Automated | pytest tests/test_payment_requests.py::test_mixed_currency_rejected_and_visibility_enforced | Critical | Passed | Yes | Amount and ISO currency pairs validated server-side
TC-P03-003 | P03 | Optimistic locking | Concurrency | Existing draft at version 1 | Update twice with the same version | First update succeeds; stale update returns HTTP 409 | Automated | pytest tests/test_payment_requests.py::test_request_crud_optimistic_lock_and_idempotent_submit | Critical | Passed | Yes | Local isolated PostgreSQL run 2026-09-08
TC-P03-004 | P03 | Idempotent submission and numbering | Integration | Valid persisted draft | Submit twice with one idempotency key | One PR-2026-six-digit number is returned both times | Automated | pytest tests/test_payment_requests.py::test_request_crud_optimistic_lock_and_idempotent_submit | Critical | Passed | Yes | Calendar-year sequence stored transactionally
TC-P03-005 | P03 | Request visibility | Security | Requests owned by users in different departments | Read another user's request without scope | HTTP 404 prevents unauthorized disclosure | Automated | pytest tests/test_payment_requests.py::test_mixed_currency_rejected_and_visibility_enforced | Critical | Passed | Yes | Owner/department/all scopes implemented
TC-P03-006 | P03 | Return for information | Workflow | Submitted Marketing request | Department Head returns with a note | Status becomes returned and immutable history is recorded | Automated | pytest tests/test_payment_requests.py::test_department_head_can_return_submitted_department_request | Critical | Passed | Yes | Local isolated PostgreSQL run 2026-09-08
TC-P03-007 | P03 | Backend regression suite | Automated | Test database at Alembic head | Run full pytest suite | All backend tests pass | Automated | pytest -q | Critical | Passed | Yes | 58 passed, 1 warning on 2026-09-22 against the dedicated test database
TC-P03-008 | P03 | Frontend production build | Build | Node dependencies installed | Run pnpm build | TypeScript and Vite production bundle succeed | Automated | pnpm run build | Critical | Passed | Yes | TypeScript and Vite 7.3.6 production build passed after mock draft fix on 2026-09-22
TC-P03-009 | P03 | General Payment business rules | Business validation | Finance-approved final rules available | Validate General Payment fields and documents | Current General Payment UI retained; final detailed rules approved | Manual | Pending Finance confirmation | High | Not Run | Yes | Pending due ambiguous P.O. wording in source sheet
TC-P03-010 | P03 | Line-total reconciliation | Financial validation | Two item lines each have one cost center and use the request currency | Create item lines with 10.0050 and 0.0050 amounts | Stored line total exactly equals the stored 10.0100 request gross amount | Automated | pytest tests/test_payment_requests.py::test_line_totals_reconcile_with_exact_four_decimal_precision | Critical | Passed | Yes | One item and one cost center per line; exact Decimal reconciliation verified 2026-09-20
TC-P03-011 | P03 | Amount precision boundary | Negative | Request payload uses more than four decimal places | Create a request with amount 1.00001 | HTTP 422 rejects unsupported precision | Automated | pytest tests/test_payment_requests.py::test_amounts_beyond_supported_precision_are_rejected | High | Passed | Yes | Pydantic and Numeric(19,4) boundary verified 2026-09-20
TC-P03-012 | P03 | Simultaneous draft edits | Concurrency | One draft and two authenticated sessions share the same version | Release both PATCH requests through one thread barrier | Exactly one update commits and the stale update returns HTTP 409 | Automated | pytest tests/test_payment_requests.py::test_simultaneous_edits_allow_exactly_one_version_to_commit | Critical | Passed | Yes | Row lock and optimistic version check verified 2026-09-20
TC-P03-013 | P03 | Duplicate submission race | Concurrency | One valid draft and one shared idempotency key | Release two submit requests simultaneously | Both calls return one identical result and create one request number | Automated | pytest tests/test_payment_requests.py::test_duplicate_submission_race_is_idempotent | Critical | Passed | Yes | Post-lock idempotency recheck verified 2026-09-20
TC-P03-014 | P03 | Concurrent request numbering | Concurrency | Six valid drafts and independent authenticated sessions | Submit all drafts simultaneously | All submissions succeed with unique contiguous academic-year numbers | Automated | pytest tests/test_payment_requests.py::test_concurrent_submissions_receive_unique_sequential_numbers | Critical | Passed | Yes | Transaction advisory lock and sequence row lock verified 2026-09-20
TC-P03-015 | P03 | Large-list pagination and performance | Performance | 130 owned request fixtures exist | Read pages 1 and 2 at 50 records per page | Stable non-overlapping pages, total metadata, bounded queries and response time under 3 seconds | Automated | pytest tests/test_payment_requests.py::test_large_request_list_is_bounded_paginated_and_query_efficient | High | Passed | Yes | Two pages completed in about 23 ms using 22 constant-count SQL statements
TC-P03-016 | P03 | Request list search, filters and sorting | API | Role-scoped request fixtures exist | Query by search, type, status, department, dates, amount and sort | Only authorized matching rows return with stable bounded pagination | Automated | pytest tests/test_payment_requests.py::test_request_list_supports_search_filters_sorting_and_amount_bounds | Critical | Passed | Yes | Server-side filters and pagination headers verified 2026-09-21
TC-P03-017 | P03 | Draft retention archival | Retention | Expired and current drafts exist in the test database | Run archive-drafts in dry-run and enabled modes | Only expired drafts are archived, audited and retained; submitted requests remain unchanged | Automated | pytest tests/test_maintenance.py | Critical | Passed | Yes | Explicit enable, dry run, batch processing and audit event verified 2026-09-21
TC-P03-018 | P03 | PHP/USD/EUR monetary boundaries | Financial validation | Valid request payloads for three currencies | Persist exact four-decimal amounts; test zero, negative and maximum values | Exact values persist; zero/negative submissions fail; supported maximum succeeds | Automated | pytest tests/test_payment_requests.py | Critical | Passed | Yes | Four-decimal persistence and amount bounds verified 2026-09-21
TC-P03-019 | P03 | Manager and privileged access authorization | Security | Manager, direct report, unrelated user and administrator exist | Read scoped requests and execute unauthorized lifecycle commands | Manager sees direct reports; unrelated access is denied; privileged reads are audited | Automated | pytest tests/test_payment_requests.py | Critical | Passed | Yes | Manager scope, explicit deny and payment_request.privileged_read audit verified 2026-09-21
TC-P03-020 | P03 | Frontend API-backed request filters | Integration | Frontend and API are running | Apply dashboard request filters and clear them | Frontend sends API query parameters and retains hybrid fallback behavior | Automated | pnpm run build; source integration review | High | Passed | Yes | Production build and API adapter mapping passed 2026-09-21
TC-P03-021 | P03 | Integrated login and dashboard | UI | API and frontend are running locally | Use Login As System Administrator and sign in | Credentials populate, login stays on the card, and API-connected dashboard renders | Manual | http://127.0.0.1:5177/#/login | Critical | Passed | Yes | Live browser verification passed 2026-09-21; existing frontend-only server was not changed
TC-P03-022 | P03 | Request API documentation | Documentation | Phase 03 API implementation is current | Review request query, lifecycle, validation, retention and error documentation | Documented contract matches implemented endpoints and maintenance controls | Manual | docs/phase-03-api.md | Medium | Passed | Yes | API contract documentation reviewed 2026-09-21
TC-P03-023 | P03 | Request API focused regression | Automated | Dedicated PostgreSQL _test database | Run focused request API suite | All request API tests pass | Automated | pytest -q tests/test_payment_requests.py | Critical | Passed | Yes | 21 passed, 1 warning on 2026-09-22
TC-P03-024 | P03 | API-connected draft persistence | UI integration | Requestor signed in to isolated test API | Save incomplete Reimbursement draft, reload, reopen from My Drafts | Purpose and department persist; backend draft appears in list | Manual | http://127.0.0.1:5184/#/requests | Critical | Passed | Yes | Synthetic QA draft deleted through API after verification
TC-P03-025 | P03 | Incomplete request feedback | UI negative | API-connected Reimbursement and mock General Payment forms | Submit empty Reimbursement line and started but incomplete General Payment line | Submission blocked with actionable line-level message | Manual | http://127.0.0.1:5184/#/requests; http://127.0.0.1:5185/#/requests | Critical | Passed | Yes | Reimbursement and General Payment messages observed
TC-P03-026 | P03 | Standalone draft reload | UI regression | Frontend in mock mode | Save a General Payment draft, reload, open My Drafts and continue editing | Draft and entered line content survive reload without API | Manual | http://127.0.0.1:5185/#/requests | High | Passed | Yes | Browser-local mock draft persistence added and verified
TC-P03-027 | P03 | Five request forms at mobile width | Responsive | Frontend in standalone mock mode | Open every request form at 390 x 844 | All forms and submit actions render without document horizontal overflow | Manual | http://127.0.0.1:5185/#/requests | High | Passed | Yes | Five form routes rendered; document scroll width 375 at width 390
TC-P03-028 | P03 | Five API-connected form routes | UI integration | Requestor signed in to isolated test API | Open each of the five request forms | Each form renders with API connected and submit action available | Manual | http://127.0.0.1:5184/#/requests | High | Passed | Yes | All five routes rendered; General Payment settled after asynchronous load
TC-P03-029 | P03 | Full browser request lifecycle | End-to-end | Safe test users and reference data | Create, edit, submit, return, resubmit, cancel and reopen all five types through the UI | Persisted states, errors and role visibility match API rules | Manual | Phase 03 browser acceptance script | Critical | Passed | Yes | Five isolated Chrome role sessions passed return, resubmit, cancel and reopen for all five request types on 2026-09-28.
TC-P03-030 | P03 | Duplicate invoice classification | Automated | Existing submitted invoice line | Submit a same-reference line with all fields equal, then one with a different amount | Complete match is tagged exact; changed information is a non-blocking Finance warning with differing fields | Automated | pytest -q tests/test_payment_requests.py -k duplicate_invoice | Critical | Passed | Yes | Invoice number comparison ignores case and whitespace; both match levels require Finance verification
TC-P03-031 | P03 | Amount and currency without conversion | Automated | Active PHP and USD currencies | Submit same-reference PHP and USD requests and inspect stored response | Entered USD amount and currency remain unchanged; no exchange-rate or converted-amount field is produced | Automated | pytest -q tests/test_payment_requests.py -k foreign_currency | Critical | Passed | Yes | Currency difference produces a non-blocking duplicate warning for Finance verification
TC-P03-032 | P03 | Authoritative P.O. eligibility and safe snapshot | Integration | Seeded Procurement P.O. and vendor adapters; Docker PostgreSQL test database | Submit an eligible P.O. payment and inspect stored type data | Backend accepts only authoritative values and stores P.O./vendor facts without bank fields | Automated | pytest -q tests/test_payment_requests.py | Critical | Passed | Yes | PO-DEMO-1001 snapshot includes eligible P.O. and VEND-DEMO-001; no bank keys
TC-P03-034 | P03 | Confirmed Cash Advance business rules | Business Rule | Docker PostgreSQL test database and requestor account | Submit over-limit, wrong due date, second outstanding advance, liquidation and retry | PHP 40,000 cap and exact 15-day date block invalid drafts; second advance is allowed only after submitted liquidation | Automated | pytest -q tests/test_payment_requests.py | Critical | Passed | Yes | Per-requestor advisory lock protects concurrent submissions
TC-P03-035 | P03 | Focused payment-request regression | Automated | Dedicated Docker PostgreSQL test database | Run the complete payment request test module | All CRUD, lifecycle, concurrency, pagination, validation and business-rule tests pass | Automated | pytest -q tests/test_payment_requests.py | Critical | Passed | Yes | 30 passed, 1 warning in 68.25 seconds
TC-P03-036 | P03 | Reimbursement Finance guidance build | Build | Current request-form frontend | Build the production frontend bundle | Timing, invoice-age, petty-cash and batch guidance compiles without changing blocking rules | Automated | pnpm run build | High | Passed | Yes | Vite 7.3.6 production build passed
TC-P03-037 | P03 | Complete Phase 00-04 backend regression | Automated | Dedicated Docker PostgreSQL 16 test database | Run the full pytest suite | All implemented backend phases pass against PostgreSQL | Automated | pytest -q | Critical | Passed | Yes | 72 passed, 1 warning in 146.36 seconds
TC-P03-038 | P03 | API-connected Procurement and Finance-guidance browser check | UI Integration | Current frontend, rebuilt API and refreshed idempotent development seed | Open P.O., Cash Advance and Reimbursement forms as the development Requestor | P.O. selector shows only current eligible API records; generated P.O. facts and confirmed Finance guidance render | Manual | http://127.0.0.1:5175/#/requests | Critical | Passed | Yes | Verified PO-DEMO-1001/1002, PHP 40,000/15-day/one-advance guidance and Reimbursement timing/petty-cash guidance
TC-P04-001 | P04 | Private document upload, preview and replacement | Integration | Editable persisted request and private MinIO bucket | Upload, list, preview and replace a document; verify version and authorization behavior | Authorized users receive the file and immutable versions; unauthorized access fails without exposing storage details | Automated | pytest -q tests/test_documents.py | Critical | Passed | Yes | Upload, listing, content streaming, replacement, duplicate warning and access controls covered
TC-P04-002 | P04 | Audited draft document removal | Automated | Owned editable request with stored document | Remove with reason and inspect list, content and storage | List excludes document, content returns gone, storage clears and metadata remains auditable | Automated | pytest -q tests/test_documents.py | Critical | Passed | Yes | Cleanup state and retry API implemented
TC-P04-003 | P04 | Required-document evaluation | Automated | Active reimbursement rule | Evaluate before and after typed upload and call submission validator | Missing requirement blocks; matching upload completes requirement | Automated | pytest -q tests/test_documents.py | Critical | Passed | Yes | Unconfigured request types remain non-blocking
TC-P04-004 | P04 | Finance hard-copy and reviewer histories | Automated | Finance Associate and uploaded document | Record hard-copy received and replacement-required decision | Current statuses and append-only history are returned | Automated | pytest -q tests/test_documents.py | High | Passed | Yes | Non-accept decisions require comments
TC-P04-005 | P04 | Document frontend build and API adapter | Build | Current document UI and data source | Run JavaScript syntax checks and production build | Build completes and mock fallback remains available | Automated | node --check; pnpm run build | High | Passed | Yes | Vite 7.3.6 production build passed
TC-P04-006 | P04 | Complete backend regression | Automated | Isolated Docker PostgreSQL 16 test database | Run full pytest and Ruff checks | All Phase 00-04 tests and lint pass | Automated | pytest -q; ruff check api migrations tests | Critical | Passed | Yes | 64 passed, 1 warning; Ruff passed on 2026-09-23
TC-P04-007 | P04 | Document regression within current full suite | Automated | Docker PostgreSQL, isolated test storage and local MinIO stack | Run full backend regression and rebuild the API container | Document lifecycle and requirement tests remain green; rebuilt API reports ready | Automated | pytest -q; docker compose up -d --build app; GET /readyz | Critical | Passed | Yes | 72-test suite passed and local API container is healthy
TC-P04-008 | P04 | General Payment conditional BIR 2303 requirement | Business Rule | Seeded General Payment requirement rules in dedicated Docker test database | Compare existing-supplier and new-supplier requirement evaluations and inspect the API requirement response | Billing / SOA / Quotation is required for both; BIR 2303 is additionally required only for a new supplier | Automated | pytest -q tests/test_documents.py | Critical | Passed | Yes | Dynamic required flag and submission gate verified; complete backend suite is 73 passed
TC-P04-009 | P04 | Unified upload controls and responsive frontend closeout | Build | Current active prototype, React parity view and responsive styles | Run JavaScript syntax, diff checks and the TypeScript/Vite production build | All upload fields use the shared accessible icon pattern; filename and document-state information remain visible; production build completes | Automated | node --check src/prototype.js; git diff --check; pnpm build | High | Passed | Yes | Request-level, line-level, add, replace, single-file and multiple-file cases use one responsive upload pattern
TC-P04-010 | P04 | Per-line Reimbursement Proof of Payment browser acceptance | UI Integration | Docker PostgreSQL 16, MinIO, seeded document rules and a two-line Reimbursement draft | Open the API-backed document workspace, upload a different Proof of Payment to each line, verify that no request-level Invoice or Billing / Quotation / SOA rule appears, inspect persisted requirements and submit | Each line displays and accepts its own required Proof of Payment; one line cannot satisfy another; no request-level reimbursement document is required; the complete request submits successfully | Automated | pnpm test:e2e -- tests/e2e/phase-04-documents.spec.js | Critical | Passed | Yes | Google Chrome click-through against disposable Docker services; both Phase 04 scenarios passed
TC-P01-020 | P01 | Current authentication and RBAC closeout | UI Integration | Rebuilt local API and synchronized deterministic seed | Sign in as Requestor, Department Head, Finance Associate, Finance Manager and System Administrator; open role-scoped pages and identity forms | All accounts authenticate; role navigation and controls match permissions; no API error appears | Manual + Automated | http://127.0.0.1:5175/#/login; pytest -q | Critical | Passed | Yes | Browser walkthrough and isolated backend regression on 2026-10-07
TC-P02-010 | P02 | Master Data functional closeout | UI Integration | Finance Manager and System Administrator accounts; API-connected frontend | Open all seven Master Data views and the applicable add forms; verify read-only vendor behavior, role controls and page overflow | Lists render without fetch errors or horizontal overflow; editable forms open; Vendors remains external/read-only | Manual + Automated | #/master-data/*; pytest -q; pnpm test:e2e | Critical | Passed | Yes | Browser-first validation and 99-test regression on 2026-10-07
TC-P03-039 | P03 | Complete request and database closeout regression | Integration | Disposable PostgreSQL 16 database | Upgrade from base to head, seed, downgrade to base, replay to head, seed and run the complete backend suite with coverage | Migration chain is reversible and deterministic; all request, concurrency and lifecycle tests pass | Automated | alembic upgrade/downgrade; pytest --cov=payment_module | Critical | Passed | Yes | 99 passed, 1 warning, 90% coverage in 322.71 seconds
TC-P04-011 | P04 | Complete headed document and responsive browser closeout | UI Integration | Disposable Docker PostgreSQL/MinIO browser-test environment | Run all lifecycle, document, settings, formatting and current-device Playwright suites | All six headed Google Chrome scenarios pass with persisted API records | Automated | pnpm test:e2e | Critical | Passed | Yes | Six suites passed in 1.5 minutes on 2026-10-07
TC-XPH-001 | P01-P04 | Dependency security and production build closeout | Security / Build | Current locked frontend and backend dependencies | Run Ruff, pnpm audit, pip-audit, TypeScript and Vite production build | No lint errors or known dependency vulnerabilities; production bundle builds | Automated | ruff check; pnpm audit --audit-level high; pip-audit; pnpm build | Critical | Passed | Yes | Patched source-map-js to 1.2.2; both audits and build passed
TC-XPH-002 | P01-P04 | Current iPhone and Samsung responsive regression | Responsive UI | Finance Manager authenticated in API-connected build | Run dashboard, tracker, approvals, settings and navigation checks across 10 representative portrait/landscape viewports | No document or main-content overflow; navigation, cards, tables and administration controls remain usable | Automated | pnpm test:e2e -- tests/e2e/responsive-current-devices.spec.js | High | Passed | Yes | 40 route/viewport combinations plus navigation and breakpoint assertions passed

## Test Executions
Test Execution History
Append-only history of test runs, actual results, defects and retest requirements.
Run ID | Test ID | Run Date | Environment | Build / Commit | Execution Status | Result | Actual Result | Executed By | Defect ID | Retest | Notes
RUN-20260825-001 | TC-P00-001 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-002 | TC-P00-002 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local Docker run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-003 | TC-P00-003 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-004 | TC-P00-004 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local Docker run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-005 | TC-P00-005 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-006 | TC-P00-006 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Supplied phase-00-propagation-test returned unchanged | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-007 | TC-P00-007 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-008 | TC-P00-008 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-009 | TC-P00-009 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-010 | TC-P00-010 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-011 | TC-P00-011 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-012 | TC-P00-012 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-013 | TC-P00-013 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local run 2026-08-25 | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-014 | TC-P00-014 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | 6 passed; 89% coverage | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-015 | TC-P00-015 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Vite 7.0.7 build passed | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-016 | TC-P00-016 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Browser verified; no console errors | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-017 | TC-P00-017 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Dashboard remained usable and showed Hybrid · mock fallback | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-018 | TC-P00-018 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Local and CI packaging passed | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-019 | TC-P00-019 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | API docs route published | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260825-020 | TC-P00-020 | 2026-08-25 | Local WSL2 / Docker Desktop / PostgreSQL 16 | 4ddd199 | Executed | Passed | Log contained method, path, status, duration_ms and request_id | Codex local audit |  | No | Evidence recorded in docs/phase-00-validation.md
RUN-20260920-001 | TC-P03-010 | 46285 | Local Windows / PostgreSQL 16 dedicated test database | f9555f2 + concurrency test changes | Executed | Passed | Exact line and request totals both stored as 10.0100 | Codex local audit |  | No | Focused suite: 13 passed
RUN-20260920-002 | TC-P03-011 | 46285 | Local Windows / PostgreSQL 16 dedicated test database | f9555f2 + concurrency test changes | Executed | Passed | Five-decimal amount rejected with HTTP 422 | Codex local audit |  | No | Focused suite: 13 passed
RUN-20260920-003 | TC-P03-012 | 46285 | Local Windows / PostgreSQL 16 dedicated test database | f9555f2 + concurrency test changes | Executed | Passed | Concurrent outcomes were one HTTP 200 and one HTTP 409 | Codex local audit |  | No | Focused suite: 13 passed
RUN-20260920-004 | TC-P03-013 | 46285 | Local Windows / PostgreSQL 16 dedicated test database | f9555f2 + concurrency test changes | Executed | Passed | Both concurrent calls returned the same number and version | Codex local audit |  | No | Focused suite: 13 passed
RUN-20260920-005 | TC-P03-014 | 46285 | Local Windows / PostgreSQL 16 dedicated test database | f9555f2 + concurrency test changes | Executed | Passed | Six simultaneous submissions received unique contiguous numbers | Codex local audit |  | No | Focused suite: 13 passed
RUN-20260920-006 | TC-P03-015 | 46285 | Local Windows / PostgreSQL 16 dedicated test database | f9555f2 + concurrency test changes | Executed | Passed | 100 records returned across two stable pages in about 23 ms; 22 SQL statements | Codex local audit |  | No | Full suite: 46 passed; Ruff passed
RUN-20260921-001 | TC-P03-016 | 46286 | Local Windows / PostgreSQL 16 dedicated test database | working tree after 1752be2 | Executed | Passed | Search/filter/sort and amount-bound API tests passed | Codex local audit |  | No | Full suite: 54 passed; Ruff passed
RUN-20260921-002 | TC-P03-017 | 46286 | Local Windows / PostgreSQL 16 dedicated test database | working tree after 1752be2 | Executed | Passed | Expired drafts archived in dry-run/enabled tests with audit evidence | Codex local audit |  | No | Submitted records were not deleted or changed
RUN-20260921-003 | TC-P03-018 | 46286 | Local Windows / PostgreSQL 16 dedicated test database | working tree after 1752be2 | Executed | Passed | PHP, USD and EUR exact values plus zero/negative/maximum boundaries passed | Codex local audit |  | No | Full suite: 54 passed
RUN-20260921-004 | TC-P03-019 | 46286 | Local Windows / PostgreSQL 16 dedicated test database | working tree after 1752be2 | Executed | Passed | Manager visibility, unauthorized commands, explicit deny and admin audit passed | Codex local audit |  | No | Full suite: 54 passed
RUN-20260921-005 | TC-P03-020 | 46286 | Local Windows / Vite 7.3.6 | working tree after 1752be2 | Executed | Passed | TypeScript and Vite production build completed successfully | Codex local audit |  | No | API adapter and hybrid fallback paths retained
RUN-20260921-006 | TC-P03-021 | 46286 | Local Windows / in-app browser / API 8002 / frontend 5177 | working tree after 1752be2 | Executed | Passed | System Administrator helper populated credentials and API-connected dashboard rendered | Codex local audit |  | No | No restoring-session page observed
RUN-20260921-007 | TC-P03-022 | 46286 | Repository documentation review | working tree after 1752be2 | Executed | Passed | Phase 03 request API and retention behavior documented | Codex local audit |  | No | docs/phase-03-api.md
RUN-20260922-001 | TC-P03-023 | 2026-09-22 | Local Windows / PostgreSQL 17 dedicated test database | working tree after 4b79603 | Executed | Passed | 21 focused request API tests passed; one warning | Codex local audit |  | No | pytest -q tests/test_payment_requests.py
RUN-20260922-002 | TC-P03-024 | 2026-09-22 | In-app Chromium / API 8004 / frontend 5184 / test DB | working tree after 4b79603 | Executed | Passed | Draft saved, reloaded and reopened with purpose and Marketing cost center | Codex browser audit |  | No | Exact synthetic draft removed through API; database count returned zero
RUN-20260922-003 | TC-P03-025 | 2026-09-22 | In-app Chromium / API and mock modes | working tree after 4b79603 | Executed | Passed | Incomplete Reimbursement and active General Payment line were blocked | Codex browser audit |  | No | Observed request-not-submitted alerts
RUN-20260922-004 | TC-P03-026 | 2026-09-22 | In-app Chromium / mock frontend 5185 | working tree after 4b79603 + mock draft fix | Executed | Passed | Draft count and entered particulars survived reload and Continue Editing | Codex browser audit |  | Completed | Retest after browser-local mock storage fix
RUN-20260922-005 | TC-P03-027 | 2026-09-22 | In-app Chromium / 390 x 844 / mock mode | working tree after 4b79603 | Executed | Passed | All five request forms had no page-level horizontal overflow | Codex browser audit |  | No | Full accessibility review separately deferred
RUN-20260922-006 | TC-P03-028 | 2026-09-22 | In-app Chromium / API 8004 / frontend 5184 | working tree after 4b79603 | Executed | Passed | All five form routes rendered with API-connected requestor session | Codex browser audit |  | No | Not a full five-type submission test
RUN-20260922-007 | TC-P03-007 | 2026-09-22 | Local Windows / PostgreSQL 17 dedicated test database | working tree after 4b79603 | Executed | Passed | Full backend regression: 58 passed, 1 warning | Codex local audit |  | No | pytest -q
RUN-20260922-008 | TC-P03-008 | 2026-09-22 | Local Windows / Vite 7.3.6 | working tree after 4b79603 + mock draft fix | Executed | Passed | TypeScript and production frontend build passed | Codex local audit |  | No | pnpm run build
RUN-20260923-001 | TC-P03-030 | 46288 | Local Windows / PostgreSQL 17 dedicated test database | working tree after 597ced1 | Executed | Passed | Exact and changed-information duplicate invoice classifications passed | Codex local audit |  | No | Focused duplicate/currency tests: 2 passed
RUN-20260923-002 | TC-P03-031 | 46288 | Local Windows / PostgreSQL 17 dedicated test database | working tree after 597ced1 | Executed | Passed | USD 1250.50 retained as USD 1250.50 with no conversion fields | Codex local audit |  | No | Focused duplicate/currency tests: 2 passed
RUN-20260923-003 | TC-P03-007 | 46288 | Local Windows / PostgreSQL 17 dedicated test database | working tree after 597ced1 | Executed | Passed | Full backend regression: 60 passed, 1 warning; Ruff passed | Codex local audit |  | No | pytest -q; ruff check api tests
RUN-20260923-004 | TC-P00-021 | 46288 | Docker Desktop 4.92.0 / Engine 29.8.0 / PostgreSQL 16 | Current working tree | Executed | Passed | Full upgrade/downgrade/replay and double seed passed | Codex local audit |  | No | docs/local-docker-acceptance-2026-09-23.md
RUN-20260923-005 | TC-P01-001 | 46288 | Current FastAPI Docker image / PostgreSQL 16 | Current working tree | Executed | Passed | Login, restart continuity, logout and post-logout rejection passed | Codex local audit |  | No | Live endpoints returned request IDs
RUN-20260923-006 | TC-P02-001 | 46288 | Disposable Docker PostgreSQL database | Current working tree | Executed | Passed | Populated table blocked removal; empty retry upgraded to head | Codex local audit |  | No | Synthetic fixture only; no production records touched
RUN-20260923-007 | TC-P00-022 | 46288 | Docker PostgreSQL 16 disposable source and restore databases | Current working tree | Executed | Passed | Custom-format restore exactly matched schema revision and sampled counts | Codex local audit |  | No | Local compatibility drill; production DR remains deferred
RUN-20260923-008 | TC-P03-007 | 46288 | Docker PostgreSQL 16 dedicated test database | Current working tree | Executed | Passed | Complete backend regression: 60 passed, 1 warning in 106.12 seconds | Codex local audit |  | No | Includes concurrency, lifecycle, pagination, performance, duplicate and currency behavior
RUN-20260923-009 | TC-P04-001 | 46288 | Docker PostgreSQL 16 / isolated test storage | Current working tree | Executed | Passed | Upload, list, preview, replacement, duplicate warning and access controls passed | Codex local audit |  | No | Focused document suite
RUN-20260923-010 | TC-P04-002 | 46288 | Docker PostgreSQL 16 / isolated test storage | Current working tree | Executed | Passed | Audited removal cleared the object and retained unavailable metadata | Codex local audit |  | No | Removal and retry state verified
RUN-20260923-011 | TC-P04-003 | 46288 | Docker PostgreSQL 16 dedicated test database | Current working tree | Executed | Passed | Requirement changed from incomplete to complete after typed upload | Codex local audit |  | No | Submission helper checked before and after upload
RUN-20260923-012 | TC-P04-004 | 46288 | Docker PostgreSQL 16 dedicated test database | Current working tree | Executed | Passed | Hard-copy received and replacement-required histories persisted | Codex local audit |  | No | Finance permission path verified
RUN-20260925-001 | TC-P03-032 | 46290 | Docker PostgreSQL 16 dedicated test database | Current working tree | Executed | Passed | Eligible P.O. submitted with immutable safe Procurement/vendor snapshot | Codex local audit |  | No | No bank-account fields retained
RUN-20260925-002 | TC-P03-033 | 46290 | Docker PostgreSQL 16 dedicated test database | Current working tree | Executed | Passed | Filed, mismatched and duplicate P.O. submissions returned field-scoped 422 responses | Codex local audit |  | No | Authoritative Procurement adapter used server-side
RUN-20260925-003 | TC-P03-034 | 46290 | Docker PostgreSQL 16 dedicated test database | Current working tree | Executed | Passed | Amount cap, due date and outstanding-advance rules passed including liquidation release | Codex local audit |  | No | Confirmed Finance rules enforced at submit/resubmit
RUN-20260925-004 | TC-P03-035 | 46290 | Local Windows / Docker PostgreSQL 16 test database | Current working tree | Executed | Passed | 30 passed, 1 warning in 68.25 seconds | Codex local audit |  | No | Focused payment-request suite
RUN-20260925-005 | TC-P03-036 | 46290 | Local Windows / Node 24 / Vite 7.3.6 | Current working tree | Executed | Passed | TypeScript and Vite production build completed successfully | Codex local audit |  | No | dist generated successfully
RUN-20260925-006 | TC-P03-037 | 46290 | Local Windows / Docker PostgreSQL 16 dedicated test database | Current working tree | Executed | Passed | 72 passed, 1 warning in 146.36 seconds | Codex local audit |  | No | Complete backend suite
RUN-20260925-007 | TC-P04-007 | 46290 | Docker PostgreSQL 16 / MinIO / rebuilt FastAPI image | Current working tree | Executed | Passed | Document regression stayed green and /readyz reported database connected | Codex local audit |  | No | Production AWS/security validation remains deferred
RUN-20260925-008 | TC-P03-038 | 46290 | In-app Chromium / API 58002 / frontend 5175 | Current working tree | Executed | Passed | Current eligible Procurement records and Finance policy guidance rendered in API-connected forms | Codex local audit |  | Completed | Initial load defect found, fixed, rebuilt and reverified
RUN-20260925-009 | TC-P04-008 | 46290 | Docker PostgreSQL 16 dedicated test database | Current working tree | Executed | Passed | Existing supplier required Billing / SOA / Quotation only; new supplier also required BIR 2303 | Codex local audit |  | No | Focused suites: 35 passed; complete suite: 73 passed; frontend build passed
RUN-20260928-001 | TC-P03-037 | 46293 | Docker PostgreSQL 16 dedicated test database | Cross-phase closeout working tree | Executed | Passed | 73 passed, 2 warnings in 20.77 seconds | Codex local audit |  | No | Migration, deterministic seed and Python compilation passed; Ruff package unavailable from configured package source
RUN-20260928-002 | TC-P04-005 | 46293 | Local Windows / Node 24 / Vite 7.3.6 | Cross-phase closeout working tree | Executed | Passed | TypeScript and Vite production build completed successfully | Codex local audit |  | No | Current responsive and unified upload changes included
RUN-20260928-003 | TC-P03-029 | 46293 | Google Chrome / dedicated payment_module_e2e PostgreSQL database | Cross-phase closeout working tree | Executed | Passed | One Playwright scenario passed in 51.5 seconds; five roles completed return, resubmit, cancel and reopen for all five request types | Codex local audit |  | No | Real UI clicks, API records and persisted lifecycle history verified
RUN-20260928-004 | TC-P04-009 | 46293 | Local Windows / active Vite server / production build | Cross-phase closeout working tree | Executed | Passed | Prototype syntax, patch integrity, Vite hot reload and production build passed | Codex local audit |  | No | Native file controls remain accessible behind the shared upload icon
RUN-20260929-001 | TC-P04-010 | 2026-09-29 | Google Chrome / Docker PostgreSQL 16 / MinIO / dedicated payment_module_e2e database | Current Phase 00-04 closeout working tree | Executed | Passed | Two Playwright scenarios passed in 24.7 seconds. The two-line Reimbursement test uploaded separate proofs, confirmed that no request-level Invoice or Billing / Quotation / SOA rule remained, and submitted the request. | Codex local audit |  | No | Production frontend build also passed; Docker test records used a disposable database
RUN-20260929-002 | TC-P04-003 | 2026-09-29 | Local Windows / Docker PostgreSQL 16 dedicated payment_module_test database | Current Phase 00-04 closeout working tree | Executed | Passed | The focused document suite completed against the isolated Docker PostgreSQL test database with 6 passed and 1 warning in 16.44 seconds, including the corrected per-line-only Reimbursement rule. | Codex local audit |  | No | pytest -q tests/test_documents.py
RUN-20261007-001 | TC-P01-020 | 46302 | Local Chrome / Docker API / PostgreSQL 16 | Phase 01-04 closeout working tree | Executed | Passed | Five core roles authenticated and opened their scoped navigation and administration views without fetch errors | Codex local audit |  | No | Stale development role-permission rows were synchronized through the idempotent seed and immediately reverified
RUN-20261007-002 | TC-P02-010 | 46302 | Local Chrome / API-connected frontend | Phase 01-04 closeout working tree | Executed | Passed | Seven Master Data pages rendered; Finance configuration and identity add forms opened; no horizontal overflow | Codex local audit |  | No | Cost centers derive from departments; Vendors remains read-only pending Procurement activation
RUN-20261007-003 | TC-P03-039 | 46302 | Local Windows / Docker PostgreSQL 16 disposable database | Phase 01-04 closeout working tree | Executed | Passed | Ruff passed; base/head migration replay and both deterministic seeds passed; 99 tests passed with 90% coverage | Codex local audit |  | No | One non-blocking warning; runtime 322.71 seconds
RUN-20261007-004 | TC-P04-011 | 46302 | Headed Google Chrome / Docker PostgreSQL 16 / MinIO | Phase 01-04 closeout working tree | Executed | Passed | All six Playwright scenarios passed in 1.5 minutes | Codex local audit |  | No | Login helpers now wait for session restoration before selecting a demo role
RUN-20261007-005 | TC-XPH-001 | 46302 | Local Windows / Node 24 / Python 3.12 | Phase 01-04 closeout working tree | Executed | Passed | pnpm and pip audits found no known vulnerabilities; TypeScript/Vite production build passed | Codex local audit | SEC-20261007-001 | Completed | source-map-js 1.2.1 advisory resolved with workspace override to 1.2.2
RUN-20261007-006 | TC-XPH-002 | 46302 | Headed Google Chrome / current-device viewport matrix | Phase 01-04 closeout working tree | Executed | Passed | Ten representative current iPhone/Galaxy portrait and landscape viewports passed across four key routes | Codex local audit |  | No | Navigation open/close, cards, tables, tabs/selectors and overflow checks passed

## Acceptance Matrix
Acceptance Matrix
Phase gates mapped to test IDs and objective evidence. A gate remains pending until every required linked test passes.
Gate ID | Phase | Gate | Acceptance Requirement | Linked Tests | Required | Result | Evidence / Limitation | Accepted Date | Accepted By
AG-P00-01 | P00 | API foundation | Liveness, readiness, discovery, versioned system route and docs are available | TC-P00-001, TC-P00-002, TC-P00-003, TC-P00-004, TC-P00-019 | Yes | Accepted | Validated locally and in CI | 2026-08-25 | Paolo Ylag
AG-P00-02 | P00 | Database foundation | PostgreSQL, migration, seed and Asia/Manila session operate repeatably | TC-P00-008, TC-P00-009, TC-P00-010, TC-P00-011, TC-P00-012 | Yes | Accepted | Validated against local PostgreSQL 16 | 2026-08-25 | Paolo Ylag
AG-P00-03 | P00 | API standards | Problem responses, request IDs, CORS and logging conventions are established | TC-P00-005, TC-P00-006, TC-P00-007, TC-P00-020 | Yes | Accepted | Request propagation, CORS and structured log fields verified | 2026-08-25 | Paolo Ylag
AG-P00-04 | P00 | Automated quality | Lint, tests, coverage and production build pass | TC-P00-013, TC-P00-014, TC-P00-015 | Yes | Accepted | 6 tests passed; 89% coverage; Vite build passed | 2026-08-25 | Paolo Ylag
AG-P00-05 | P00 | Delivery packaging | Docker image builds and both Compose services become healthy | TC-P00-008, TC-P00-018 | Yes | Accepted | Local Docker and GitHub package job passed | 2026-08-25 | Paolo Ylag
AG-P00-06 | P00 | Continuously runnable prototype | Hybrid frontend connects to API and falls back safely when API is unavailable | TC-P00-016, TC-P00-017 | Yes | Accepted | API connected and Hybrid · mock fallback states both verified | 2026-08-25 | Paolo Ylag
AG-P03-01 | P03 | Request API integrity | Persisted requests enforce lifecycle, ownership, currency, concurrency and totals | TC-P03-001 to TC-P03-008; TC-P03-010 to TC-P03-019; TC-P03-023; TC-P03-030 to TC-P03-035; TC-P03-037 | Yes | Accepted | 99-test Docker/PostgreSQL regression, reversible migration replay, deterministic seed and 90% coverage passed. | 2026-10-07 | Paolo Ylag
AG-P03-02 | P03 | Browser request lifecycle | All five types complete valid and invalid UI lifecycle flows in API and standalone modes | TC-P03-024 to TC-P03-029; TC-P03-036; TC-P03-038 | Yes | Accepted | Five-role lifecycle for all five request types and the complete six-scenario headed Chrome suite passed. | 2026-10-07 | Paolo Ylag
AG-P03-03 | P03 | Finance business rules | Final General Payment and Cash Advance policy decisions are confirmed | TC-P03-009; TC-P03-030 to TC-P03-034; TC-P04-008 | Yes | Accepted | Confirmed duplicate, no-conversion, Cash Advance, batch, and General Payment rules are implemented and tested; deferred cash-out exceptions remain an accepted limitation. | 2026-10-07 | Paolo Ylag
AG-P04-01 | P04 | Local document lifecycle | Private upload, preview, replacement, removal, requirements and audit controls pass | TC-P04-001 to TC-P04-004; TC-P04-006 to TC-P04-008 | Yes | Accepted | Private document lifecycle, requirements, versioning, hard-copy/review histories and full regression passed. | 2026-10-07 | Paolo Ylag
AG-P04-02 | P04 | Frontend document workflow | API-backed document operations and standalone fallback pass browser acceptance | TC-P04-005 | Yes | Accepted | Five-role document workflow, multi-line Reimbursement uploads, responsive upload UI and production build passed. | 2026-10-07 | Paolo Ylag
AG-P04-03 | P04 | Production document controls | AWS, malware, retention and final Finance rule configuration are approved and validated | Production validation plan | No | Deferred to Phase 09 | Production S3/IAM, malware scanning, retention and hosted accessibility are explicitly outside local Phase 04 acceptance. | 2026-10-07 | Paolo Ylag
AG-P01-01 | P01 | Current identity and RBAC regression | Authentication, sessions, role navigation and protected identity administration remain correct in the current build | TC-P01-020 | Yes | Accepted | Five-role browser walkthrough and 99-test backend regression passed | 2026-10-07 | Paolo Ylag
AG-P02-01 | P02 | Local Master Data lifecycle | All seven Master Data views and authorized configuration controls work against persisted reference data | TC-P02-010 | Yes | Accepted | Browser-first functional checks, API regression and production build passed | 2026-10-07 | Paolo Ylag
AG-P02-02 | P02 | External reference-data activation | Authoritative Finance values and live Procurement vendor transport are supplied before production use | Phase 09 production validation plan | No | Deferred to Phase 09 | Deterministic local data is accepted for development; production activation remains external | 2026-10-07 | Paolo Ylag

## Instructions
Workbook Maintenance Guide
Use this workbook as the QA system of record for development phases and repeatable acceptance decisions.
Step | When | Action | Sheet | Required Fields | Rule
1 | A work item starts | Add or update its development row | Development Log | Phase, work item, status, branch, owner | Do not mark Complete without evidence
2 | A requirement is testable | Create a stable test ID | Test Cases | Steps, expected result, priority, acceptance flag | Never recycle test IDs
3 | A test is executed | Append a new run | Test Executions | Run ID, date, build, result, evidence | Never overwrite historical runs
4 | A defect is found | Record the defect and retest requirement | Test Executions | Defect ID, result, retest | Failed acceptance tests block the gate
5 | A gate is reviewed | Confirm linked required tests | Acceptance Matrix | Result, evidence, accepted date/by | Pending if any required test is not passed
6 | A phase is approved | Update the phase ledger | Phase Register | Status, validation reference, date | Use Validated only after acceptance review
7 | A release/build changes | Create fresh execution rows | Test Executions | New build/commit and actual result | Re-run affected regression tests
Controlled field | Allowed values
Phase Status | Not Started; In Progress; Ready for Validation; Validated; Blocked
Test Result | Not Run; Passed; Failed; Blocked; N/A
Priority | Critical; High; Medium; Low
Acceptance Result | Pending; Accepted; Rejected; Blocked
Retest | No; Required; Completed
Evidence | Command output, URL, CI run, screenshot, log, commit or document reference